## SI
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Sprint | Sprint Schedule | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#1 | 2025-03-03 ~ 2025-03-26 | 10 | 10 | 21 | 21 | 100% | 2.1 | 100% | 16 out of 18 tasks have been completed successfully. All 16 identified defects have been resolved.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#2 | 2025-04-08 ~ 2025-05-02 | 8 | 8 | 8 | 8 | 100% | 1 | 100% | All tasks (11) have been completed. 6 defects were detected and have been fully fixed.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#3 | 2025-05-05 ~ 2025-06-25 | 20 | 18 | 12 | 10 | 90% | 0.66667 | 83.33% | 2 Tasks and 2 Issues are carried over and completed on Sprint 4
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#4 | 2025-06-02 ~ 2025-07-02 | 20 | 16 | 22 | 22 | 80% | 1.375 | 100% | 4 Tasks are carried over to Sprint 5. (3 completed, 1 carried over again to Sprint 6)
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#5 | 2025-07-02 ~ 2025-08-01 | 27 | 17 | 28 | 24 | 62.96% | 1.6471 | 85.71% | 10 Tasks and 4 Bugs are carried over to Sprint 6
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#6 | 2025-07-02 ~ 2025-08-01 | 17 | 17 | 31 | 31 | 100% | 1.8235 | 100% | 12 Story and 5 taks have been completed , and 31 defect already fixed. this is last sprint before Job portal going to System Maintenance (SM) project.
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#1 | 2025-04-21 ~ 2025-04-25 | 265 | 265 | 41 | 41 | 100% | 0.15472 | 100% | Sprint #1 - Testing Scenario: Scenario received on May 25, completed on June 25 Total scenarios: 269 Executed: 265 In Progress: 0 Passed: 222 Failed: 41
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#2 | 2025-04-21 ~ 2025-04-25 | 855 | 855 | 28 | 28 | 100% | 0.032749 | 100% | Sprint #2 Total scenarios: 855 Executed: 828 Passed: 776 Failed: 28 Blocked : 24 Untested : 27
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#3 | 2025-06-30 ~ 2025-08-14 | 730 | 730 | 1 | 1 | 100% | 0.0013699 | 100% | Sprint #3 Total scenarios: 730 Executed: 729 Passed: 729 Failed: 1
| [Bank Sinarmas] Provision of Card Management System Services | [LDC] Bank Sinarmas |  |  | Andini Margaretta Tarigan |  | SI | S#1 | 2025-09-01 ~ 2025-10-03 | 215 | 241 | 0 | 0 | 112.1% | 0 | #DIV/0! | [Cumulative] - Authorization/Common part : Plan = 72 ¦ Actual = 77 - Front part : Plan = 70 ¦ Actual = 92 - Back-end part : Plan = 73 ¦ Actual = 72 (There was a delay in reflecting the brand incoming file due to work reference checks) Overall Progress = 37.8%
| [Bank Sinarmas] Provision of Card Management System Services | [LDC] Bank Sinarmas |  |  | Andini Margaretta Tarigan |  | SI | S#2 | 2025-10-04 ~ 2025-12-04 | 679 | 656 | 0 | 0 | 97% | 0,00 | N/A | [Cumulative Progress] - Authorization/Common part : Plan = 199 ¦ Actual = 203 - Front part : Plan = 184 ¦ Actual = 181 - Back-end part : Plan = 192 ¦ Actual = 188 - Bank Sinarmas : Plan = 104 ¦ Actual = 87 Overall Progress = 91%

## January
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 8 | 7 | 0 | 0 | 87.5% | 0 | #DIV/0! | 7 out of 8 tasks were completed, with no defects reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 2 | 2 | 0 | 0 | 100% | 0 | #DIV/0! | SF Core is not yet fully using Wire-Work for Task Tracking Management
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | All 14 tasks were completed without any defect occurrences.

## February
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 8 | 7 | 0 | 0 | 87.5% | 0 | #DIV/0! | 7 of 8 tasks have been completed. No defects were found during this sprint.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 3 | 3 | 0 | 0 | 100% | 0 | #DIV/0! | All assigned tasks were completed successfully with zero defects reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 8 | 8 | 0 | 0 | 100% | 0 | #DIV/0! | Full task completion achieved with no bugs identified.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | 100% workload completed with clean execution and no defects recorded.

## March
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 6 | 5 | 0 | 0 | 83.33% | 0 | #DIV/0! | 5 out of 6 tasks were completed, showing solid progress with no defects reported.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 24 | 24 | 0 | 0 | 100% | 0 | #DIV/0! | 100% task completion (24/24). No defects found.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 19 | 18 | 0 | 0 | 94.74% | 0 | #DIV/0! | 18 of 19 tasks completed. All with zero defects.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 7 | 7 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks completed (7/7).

## April
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 9 | 8 | 0 | 0 | 88.89% | 0 | #DIV/0! | 8 of 9 tasks completed. Smooth progress with no defects.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | 100% completion. No issues encountered.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 28 | 28 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks delivered successfully.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 57 | 57 | 0 | 0 | 100% | 0 | #DIV/0! | No defects across all 57 tasks.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 16 | 16 | 0 | 0 | 100% | 0 | #DIV/0! | Full task completion. Testing went flawlessly.

## May
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 10 | 10 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks were completed successfully without any defects reported.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 42 | 42 | 0 | 0 | 100% | 0 | #DIV/0! | Project achieved full delivery with no quality issues encountered.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 7 | 7 | 1 | 1 | 100% | 0.14286 | 100% | All tasks delivered, with 1 defect discovered and promptly resolved.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 18 | 18 | 0 | 0 | 100% | 0 | #DIV/0! | Project completed without any technical issues or defects.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 37 | 37 | 0 | 0 | 100% | 0 | #DIV/0! | The sprint ended with 100% completion and no bugs recorded.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 119 | 119 | 0 | 0 | 100% | 0 | #DIV/0! | 119 task completed with 12 defects identified

## June
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 13 | 11 | 0 | 0 | 84.62% | 0 | #DIV/0! | 11 out of 13 tasks were completed. No defects were reported.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 60 | 60 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks completed successfully. 28 defects resolved during the sprint.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 13 | 13 | 0 | 0 | 100% | 0 | #DIV/0! | Project completed with full delivery and no issues encountered.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 50 | 49 | 1 | 1 | 98% | 0.020408 | 100% | Nearly all tasks were finished. 1 defect was identified and fixed.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 26 | 26 | 0 | 0 | 100% | 0 | #DIV/0! | 100% completion with no defects.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 5 | 5 | 0 | 0 | 100% | 0 | #DIV/0! | All 5 tasks completed. No issues encountered.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 131 | 131 | 23 | 23 | 100% | 0.17557 | 100% | High workload accomplished. 23 defects were reported.

## July
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 11 | 9 | 2 | 2 | 81.82% | 0.22222 | 100% | 9 out of 11 tasks were completed. 2 defects were reported and all fixed.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 83 | 82 | 0 | 0 | 98.8% | 0 | #DIV/0! | 82 out of 83 tasks were completed, mostly do defect fixing
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 5 | 5 | 0 | 0 | 100% | 0 | #DIV/0! | All 5 tasks were completed. No defects were reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 193 | 185 | 20 | 20 | 95.85% | 0.10811 | 100% | 185 out of 193 tasks were completed. 20 defects were reported and all fixed.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 58 | 58 | 0 | 0 | 100% | 0 | #DIV/0! | All 58 tasks were completed. No defects were reported.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 14 | 13 | 0 | 0 | 92.86% | 0 | #DIV/0! | 13 out of 14 tasks were completed. No defects were reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 148 | 143 | 0 | 0 | 96.62% | 0 | #DIV/0! | 143 out of 148 tasks were completed. 7 defects were reported
| KB Bank System Maintenance | [GDC] SHINE NGBS |  |  | Andhika Putra | 9 | SM | 44 | 40 | 1 | 1 | 90.91% | 0.025 | 100% | 40 out of 44 tasks were completed. 1 defect was reported and fixed.

## August
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 2 | SM | 10 | 9 | 1 | 1 | 90% | 0.11111 | 1 | 9 out of 10 tasks were completed. 1 defect was reported and fixed. unfinish task : 1 tasks is because cannot be replicate the task on dev environment.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 109 | 105 | 0 | 0 | 96.33% | 0 | #DIV/0! | 105 out of 109 tasks were completed. No defects were reported. Workload mostly involved fixing 89 bugs and developing 20 tasks.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 55 | 50 | 0 | 0 | 90.91% | 0 | #DIV/0! | 50 out of 55 tasks were completed. No defects were reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 238 | 231 | 6 | 6 | 97.06% | 0.025974 | 1 | 231 out of 238 tasks were completed. 6 defects were reported and all fixed.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 73 | 71 | 2 | 2 | 97.26% | 0.028169 | 1 | 71 out of 73 tasks were completed. 2 defects were reported and all fixed.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 6 | 6 | 0 | 0 | 100% | 0 | #DIV/0! | All 6 tasks were completed. No defects were reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 147 | 147 | 20 | 20 | 100% | 0.13605 | 1 | 20 defects found earlier, 18 already fixed, 2 still being resolved by developer.
| KB Bank System Maintenance | [GDC] SHINE NGBS |  |  | Andhika Putra | 9 | SM | 18 | 18 | 0 | 0 | 100% | 0 | #DIV/0! | All 18 tasks were completed.

## September
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Period | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 1 Sep ~ 3 Oct 2025 | 73 | 71 | 0 | 0 | 97.26% | 0 | #DIV/0! | Finish 26 task and 47 fixing defect
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 28 Aug ~ 3 Sep 2025 | 43 | 43 | 0 | 0 | 100% | 0 | #DIV/0! | Finish 32 Task and 11 Story, no defect found
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 28 Aug ~ 3 Sep 2025 | 263 | 247 | 9 | 9 | 93.92% | 0.036437 | 100% | 247 out of 263 tasks were completed. 9 defects were reported and all have been fixed.
| SF Manufacture DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 28 Aug ~ 3 Sep 2025 | 7 | 7 | 0 | 0 | 100% | 0 | #DIV/0! | All 7 tasks were completed. No defects were reported.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 28 Aug ~ 3 Sep 2025 | 103 | 101 | 1 | 1 | 98.06% | 0.009901 | 100% | 101 out of 103 tasks were completed. 1 defect was reported and fixed.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 28 Aug ~ 3 Sep 2025 | 1 | 1 | 0 | 0 | 100% | 0 | #DIV/0! | 1 out of 1 task was completed. No defects were reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 1 Sep ~ 3 Oct 2025 | 155 | 150 | 1 | 1 | 96.77% | 0.0066667 | 100% | 150 out of 155 tasks were completed. 1 defect was reported and fixed.
| KB Bank System Maintenance | [GDC] SHINE NGBS |  |  | Doddy Poerwo Haryadi | 9 | SM | 1 Sep ~ 3 Oct 2025 | 64 | 62 | 5 | 5 | 96.88% | 0.080645 | 100% | 62 out of 64 tasks were completed. 5 defects were reported and all have been fixed.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | - | SM | 1 Sep ~ 3 Oct 2025 | 35 | 35 | 28 | 28 | 100% | 0.8 | 100% | Resolved 28 bugs. Completed 13 user stories. Finished 2 tasks and 20 sub-tasks.

## November
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Period | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 4 Nov ~ 7 Dec 2025 | 58 | 58 | 0 | 0 | 100% | 0% | #DIV/0! | All assigned tasks have been completed: 15 tasks and 43 bugs resolved.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 30 Oct ~ 4 Dec 2025 | 77 | 75 | 0 | 0 | 97.4% | 0 | #DIV/0! | Completed 75 out of 77 tasks, 2 task still in progress
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 30 Oct ~ 4 Dec 2025 | 106 | 89 | 8 | 8 | 83.96% | 0.089888 | 100% | 8 bug, 2 task in checking, 2 in progress, 8 in test by korean team
| SF Manufacture DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 30 Oct ~ 4 Dec 2025 | 4 | 4 | 0 | 0 | 100% | 0 | #DIV/0! | All 4 tasks were completed. No defects were reported.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 30 Oct ~ 4 Dec 2025 | 148 | 110 | 4 | 4 | 74.32% | 0.036364 | 100% | Most of the tasks are repetitive, and the deadline is still well ahead. 110 task done, 38 Task is In progress / In development"
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 30 Oct ~ 4 Dec 2025 | 2 | 2 | 0 | 0 | 100% | 0 | #DIV/0! | All 2 tasks were completed. No defects were reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 4 Nov ~ 5 Dec 2025 | 120 | 120 | 8 | 8 | 100% | 0.066667 | 100% | 120 SSR tickets have been completed for testing. Among of them, 8 defects were found, defect tickets have been created, and the issues have been fixed by the developer
| KB Bank System Maintenance | [GDC] SHINE NGBS | 2025-01-01 | 2025-12-31 | Doddy Poerwo Haryadi | 9 | SM | 4 Nov ~ 5 Dec 2025 | 79 | 73 | 1 | 1 | 92.41% | 0.013699 | 100% | 73 out of 79 tasks were completed. 1 defect were reported and have been fixed.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 12 | SM | 3 Nov ~ 3 Dec 2025 | 45 | 45 | 19 | 19 | 100% | 0.42222 | 100% | Resolved 19 bugs. Completed 8 user stories. Finished 37 sub-tasks.

## December
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Period | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 4 Nov ~ 7 Dec 2025 | 68 | 68 | 0 | 0 | 100% | 0% | #DIV/0! | All assigned tasks have been completed: 68 out of 68 tasks completed. No defects were found during this period.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian, Willy Candra Sugianto | 11 | SM | 30 Oct ~ 4 Dec 2025 | 131 | 106 | 0 | 0 | 80.92% | 0 | #DIV/0! | 106 out of 131 planned tasks have been completed. The remaining tasks are still in progress. No defects were reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 30 Oct ~ 4 Dec 2025 | 178 | 171 | 18 | 13 | 96.07% | 0.10526 | 72.22% | 171 out of 178 planned tasks have been completed.
| SF Manufacture DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 30 Oct ~ 4 Dec 2025 | 10 | 8 | 0 | 0 | 80% | 0 | #DIV/0! | 4 out of 10 planned tasks have been completed. The remaining tasks are in progress. No defects were found.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 30 Oct ~ 4 Dec 2025 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | No tasks were assigned during this period.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 30 Oct ~ 4 Dec 2025 | 172 | 56 | 4 | 4 | 32.56% | 0.071429 | 100% | 56 out of 172 planned tasks have been completed. 4 defects were found and all have been successfully resolved.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 4 Nov ~ 5 Dec 2025 | 124 | 124 | 14 | 14 | 100% | 0.1129 | 100% | 120 SSR tickets have been completed for testing. Among of them, 8 defects were found, defect tickets have been created, and the issues have been fixed by the developer
| KB Bank System Maintenance | [GDC] SHINE NGBS | 2025-01-01 | 2025-12-31 | Doddy Poerwo Haryadi | 9 | SM | 4 Nov ~ 5 Dec 2025 | 149 | 145 | 0 | 0 | 97.32% | 0 | #DIV/0! | 145 out of 149 planned tasks have been completed. The remaining tasks are in progress. No defects were reported.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 12 | SM | 3 Nov ~ 3 Dec 2025 | 189 | 149 | 50 | 33 | 78.84% | 0.33557 | 66% | Resolved 19 bugs. Completed 8 user stories. Finished 37 sub-tasks.

## Quality Metrics
Project Type | Project evaluation will be conducted based on comprehensive "Project Quality Metrics," with the update frequency and evaluation approach tailored to the project type:
SI | For SI (System Integration) projects, which involve building a new system from scratch, evaluations will be updated after every sprint to closely monitor development progress, quality, and issue resolution during incremental delivery phases.
SM | For SM (System Maintenance) projects, focused on maintaining and improving existing systems, evaluations will be updated monthly, allowing a broader view of ongoing system health and maintenance activities over time.
Quality Metrics
Indicator | Productivity Rate | Quality Rate
| Function Fulfilment Evaluation | Bug Density | Bug Correction Rate
Risk | Completed requests ≤ 70% | Bug density ≥ 3 or Bug correction rate ≤ 70%
Issue | Completed requests ≥ 70% and < 80% | Bug density ≥ 2 or Bug correction rate > 70% and ≤ 80%
Standard | Completed requests ≥ 80% | Bug density < 2 or Bug correction rate > 80%
Metric Definitions and Impact on Project Types
Functional Fulfillment: | Measures how much of the requested functions have been completed relative to the total planned functions for the project or component.
Bug Density | Number of bugs found relative to the size of the project/component - critical for both new development (SI) and ongoing maintenance (SM).
Bug Correction Rate: | Percentage of bugs fixed within the evaluated period, indicating responsiveness and maintenance quality.