## in
Issue Type | Project key | Project name | Project type | Project lead | Project lead id | Project description | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Status Category | Created | Updated | Resolution | Resolved | Sprint | Sprint | Sprint
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3336 | 232731 | Edit response on delivery API | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | CODE REVIEW | In Progress | 01/Sep/25 2:53 AM | 02/Sep/25 8:33 AM
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3292 | 232243 | Create Address API for express checkout | Yawei (Sigma) Yang / LGE | 712020:aeff2087-24ad-485b-9b90-c2b597d080f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Medium | CODE REVIEW | In Progress | 28/Aug/25 2:30 PM | 29/Aug/25 4:13 PM
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3263 | 232147 | [STG] Express checkout / Checkout: Next day & Expediated delivery options missing for all Parcel products | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR QA | In Progress | 28/Aug/25 4:53 AM | 02/Sep/25 8:35 AM |  |  | PFO Sprint 13
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3258 | 232115 | Handle product sku STORE on query param level | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | CODE REVIEW | In Progress | 27/Aug/25 11:05 PM | 28/Aug/25 8:36 AM
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3253 | 232010 | zipcode 94043 , 11010 should not be restricted ESP item. | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | Low | Done | Done | 27/Aug/25 1:57 PM | 27/Aug/25 6:17 PM | Done | 27/Aug/25 6:17 PM | PFO Sprint 12
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3245 | 231821 | API to get schedule details | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | CODE REVIEW | In Progress | 26/Aug/25 4:59 PM | 27/Aug/25 6:00 PM
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3243 | 231779 | [TASK] Delivery Message for LMD on PDP and Cart – Carrier Down Fallback Handling | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | High | READY FOR QA | In Progress | 26/Aug/25 2:48 PM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3231 | 231725 | API Improvements for Quote API | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | CODE REVIEW | In Progress | 26/Aug/25 8:53 AM | 02/Sep/25 8:33 AM
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3224 | 231712 | [QA10] [PM] - On Checkout : Expediated delivery method is not shown for any parcel product | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR QA | In Progress | 26/Aug/25 7:30 AM | 02/Sep/25 8:36 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3223 | 231709 | [QA10][PM] [EOS] Express Checkout - Unable to place BOPIS order | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | Hema Deepika Rani / Qualitest | 623e01d4a2f6400069ec7fe6 | High | Done | Done | 26/Aug/25 7:26 AM | 26/Aug/25 2:35 PM | Done | 26/Aug/25 2:35 PM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3208 | 231673 | [QA10] [OBS Guest] /EOS Express Checkout - Date discrepancy for standard and expedited delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Hema Deepika Rani / Qualitest | 623e01d4a2f6400069ec7fe6 | High | RE-OPENED | To Do | 26/Aug/25 3:31 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3076 | 227683 | [QA10] Dynamic Scheduling : LMD Next day delivery is showing todays delivery date | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 21/Aug/25 4:13 AM | 29/Aug/25 1:15 PM | Done | 25/Aug/25 8:46 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-3012 | 227002 | [QA10] [OBS Guest] Express Checkout - Date discrepancy for Next Day In-home delivery | Hema Deepika Rani / Qualitest | 623e01d4a2f6400069ec7fe6 | Hema Deepika Rani / Qualitest | 623e01d4a2f6400069ec7fe6 | High | READY FOR STAGING | Done | 20/Aug/25 2:12 AM | 26/Aug/25 8:48 AM | Done | 26/Aug/25 3:30 AM | PFO Sprint 12
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2982 | 226781 | API to get options for delivery. | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Critical | READY FOR QA | In Progress | 19/Aug/25 9:47 AM | 27/Aug/25 10:17 PM
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2969 | 226746 | Handle error response on Quote Validate API | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | Done | Done | 19/Aug/25 7:35 AM | 26/Aug/25 11:13 PM | Done | 26/Aug/25 3:52 PM | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2926 | 220662 | [QA10] [No Remove Stre Credit Option] PayPal payment is available after applying store credits | Akash Suryawanshi / Qualitest | 712020:c64b05e6-39f0-4401-8423-333d5b4d4dca | Akash Suryawanshi / Qualitest | 712020:c64b05e6-39f0-4401-8423-333d5b4d4dca | Critical | READY FOR QA | In Progress | 17/Aug/25 9:42 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2839 | 220410 | [QA10] Delivery Service: snapshot API: Delivery Date Null For Specific Zip code | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | Pawan Bhandari / Qualitest | 61813ae75800630069e5e178 | Blocker | READY FOR QA | In Progress | 15/Aug/25 9:09 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2801 | 220177 | Get Slot POST API | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | READY FOR QA | In Progress | 14/Aug/25 3:32 AM | 26/Aug/25 11:12 PM |  |  | PFO Sprint 13
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2800 | 220173 | Add missing field for request estimate date to FedEx | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | Done | Done | 14/Aug/25 3:04 AM | 26/Aug/25 11:06 PM | Done | 26/Aug/25 3:53 PM | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2633 | 218552 | [QA10][MS] Get Cart: Standard method not available on available delivery option | Xiaoxue Guo / Marlabs | 712020:88f292a2-1061-472e-ba4f-e4d87354e48e | Xiaoxue Guo / Marlabs | 712020:88f292a2-1061-472e-ba4f-e4d87354e48e | High | Done | Done | 09/Aug/25 4:51 PM | 26/Aug/25 11:16 PM | Done | 25/Aug/25 9:31 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2580 | 218183 | [QA10][Delivery API] - Quote API - getting availabilty :False if qnty is more than 1 For "PARCEL"with : "NEXT_DAY" delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 08/Aug/25 3:38 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 10:48 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2578 | 218181 | [QA10][Delivery API] - Quote API - getting availabilty :False if qnty is more than 1 For "PARCEL"with : "EXPEDITED" delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 08/Aug/25 3:32 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 11:05 AM | PFO Sprint 11
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2570 | 218123 | Merge Repos into process layer | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | Done | Done | 07/Aug/25 4:53 PM | 26/Aug/25 11:05 PM | Done | 26/Aug/25 3:54 PM
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2564 | 217981 | [QA10][Delivery API] - Quote API - Incorrect estimated delivery date for For "PARCEL"with : "EXPEDITED" delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 07/Aug/25 7:58 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 3:29 AM | PFO Sprint 11
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2485 | 216596 | Implement Product Type Restriction | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Low | RE-OPENED | To Do | 05/Aug/25 11:42 PM | 02/Sep/25 1:09 AM
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2481 | 216484 | [QA10] [ORD][MS ] Set payment method: Store credit with Paypal is allowed into Set payment method | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 05/Aug/25 2:33 PM | 19/Aug/25 11:36 AM | Done | 11/Aug/25 5:08 AM
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2474 | 216365 | [QA10] [ORD][MS ] Set payment method: Getting 400 error with incorrect message if We pass "reward_points" option for Guest user cart ID | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Low | READY FOR STAGING | Done | 05/Aug/25 10:06 AM | 01/Sep/25 10:03 AM | Done | 01/Sep/25 10:03 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2421 | 215247 | [QA10][Delivery API] - Quote API & Validate API - "vendorIdentifier" feild is mandatory and accept any test data into it | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 31/Jul/25 10:20 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 10:42 AM | PFO Sprint 11
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2396 | 215024 | [MS][DS] - inventory API need provide the openBoxQty | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Yawei (Sigma) Yang / LGE | 712020:aeff2087-24ad-485b-9b90-c2b597d080f0 | Critical | Done | Done | 31/Jul/25 12:18 AM | 18/Aug/25 8:53 AM | Done | 09/Aug/25 12:08 PM | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2381 | 214111 | [QA10][Delivery API] - Quote API - availability: false with unexpcted error For "PARCEL"with : "EXPEDITED" as Fedx api giving 500 response | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 30/Jul/25 7:56 AM | 29/Aug/25 1:11 PM | Done | 25/Aug/25 3:13 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2369 | 214052 | [QA10][Product service] - "GET product Inventory by SKU API "For Incorrect Warehouse code & valid SKU ID getting 200 response with blank response body | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | Done | Done | 30/Jul/25 2:39 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 4:09 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2367 | 214046 | [QA10][Product service] - "GET product Inventory by SKU API "For Incorrect SKU ID getting 400 response with Internal server error message | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 30/Jul/25 1:59 AM | 01/Sep/25 9:59 AM | Done | 01/Sep/25 9:59 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2361 | 213873 | [QA10][Delivery API] - Quote API - Incorrect estimated delivery date for For "PARCEL"with : "EXPEDITED" if Current time of warehouse(6.40) & Cutoff time (6) is same | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 29/Jul/25 2:27 PM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 6:41 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2354 | 213350 | [QA10][Delivery API] - Quote API - Incorrect estimated delivery cost for For "PARCEL"with : "NEXT_DAY" / "EXPEDITED" delivery - both cost are standard fedx delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 29/Jul/25 10:00 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 12:19 PM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2353 | 213331 | [QA10][Delivery API] - Quote API - Incorrect estimated delivery date for For "PARCEL"with : "NEXT_DAY" delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 29/Jul/25 9:29 AM | 19/Aug/25 11:36 AM | Done | 08/Aug/25 2:51 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2265 | 212180 | [QA10][Delivery API] - For some SKU getting Unexpected Error into response with 200 response code for Quote API with "freightType": "PARCEL" & "shippingMethod": "NEXT_DAY" / EXPEDETED | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 25/Jul/25 6:04 AM | 19/Aug/25 11:37 AM | Done | 28/Jul/25 9:56 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2247 | 211913 | [QA10][Delivery API] - For Quote API with "freightType": "LMD" & Shipping method: standard - getting Data not found error (404) | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 24/Jul/25 10:24 AM | 19/Aug/25 11:36 AM | Done | 16/Aug/25 7:02 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2227 | 211622 | [QA10][Delivery API] - "Validate" API getting response false for PARCEL method with 2 products but from different warehouse | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | Done | Done | 23/Jul/25 2:23 PM | 19/Aug/25 11:36 AM | Done | 25/Jul/25 4:40 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2224 | 211600 | [QA10][Delivery API] - For Quote API : PARCEL with NEXT-DAY/ EXPEDIATE when added invalid or expired token got 200 response with availability false and error into response body | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 23/Jul/25 1:14 PM | 19/Aug/25 11:36 AM | Done | 28/Jul/25 12:43 PM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2222 | 211504 | [QA10][Delivery API] - Quote API :if we add more than 1 SKU into payload of "PARCEL"with : "NEXT_DAY" or "EXPEDITED" delivery then inresponse getting wrong SKU & Qauntity details | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 23/Jul/25 10:13 AM | 19/Aug/25 11:36 AM | Done | 28/Jul/25 10:15 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2218 | 211400 | [QA10][Delivery API] - Quote API - Incorrect estimated cost if more than 1 quantity For "PARCEL"with : "NEXT_DAY" or "EXPEDITED" delivery | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 23/Jul/25 9:03 AM | 19/Aug/25 11:36 AM | Done | 25/Jul/25 7:46 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2213 | 211314 | [QA10][Delivery API] - Need info : If delivery service / carrier api is down then how to check and what error we will throw from api | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 23/Jul/25 6:52 AM | 29/Aug/25 1:11 PM | Done | 25/Aug/25 3:16 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2212 | 211313 | [QA10][Delivery API] - Quote API For "PARCEL"with : "NEXT_DAY" or "EXPEDITED" delivery getting same estimate date of standard shipping (Incorrect delivery date) | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 23/Jul/25 6:42 AM | 19/Aug/25 11:36 AM | Done | 28/Jul/25 10:21 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2188 | 211043 | QA10 [Delivery-API] : Quote API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | NEED MORE INFO | In Progress | 22/Jul/25 9:40 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2186 | 211004 | [QA10][Delivery API] - For Quote API with "freightType": "PARCEL" & "shippingMethod": "STANDARD" getting incorrect estimate date & Days | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 22/Jul/25 7:14 AM | 19/Aug/25 11:35 AM | Done | 23/Jul/25 3:37 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2185 | 210991 | QA10 [Delivery-API] : Estimate API for PLP page is giving incorret estimateDate & days | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 22/Jul/25 6:40 AM | 19/Aug/25 11:35 AM | Done | 23/Jul/25 3:27 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2182 | 210966 | [QA10][Delivery API] - For PLP API with 96161 Zipcode getting Null estimated date for PARCEL & LMD freight type | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | To Do | To Do | 22/Jul/25 3:51 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2180 | 210955 | [QA10][Delivery API] - For Quote API with "freightType": "LMD" & 96161/32789/90001/34433/33890 zip code got error against estimated delivery & available:False though stock is available in respective warehouse | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 22/Jul/25 2:06 AM | 19/Aug/25 11:35 AM | Done | 28/Jul/25 11:57 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2167 | 210730 | [QA10][Delivery API] - For Quote API with invalid or expired token got 200 response with availability false and error into response body | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 21/Jul/25 8:28 AM | 19/Aug/25 11:35 AM | Done | 22/Jul/25 10:37 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2141 | 210241 | [QA10][Delivery API] - For Quote API with "freightType": "LMD" & RXO zip code got error against estimated delivery & available:False though stock is available in respective warehouse | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 18/Jul/25 9:13 AM | 19/Aug/25 11:37 AM | Done | 22/Jul/25 1:44 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2139 | 210214 | [QA10][Delivery API] - For Quote API with "freightType": "LMD" & "shippingMethod": "NEXT_DAY" getting same estimate date of standard shipping | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 18/Jul/25 7:04 AM | 26/Aug/25 11:04 PM | Done | 16/Aug/25 2:57 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2126 | 210181 | [QA10][Delivery API] - Getting Error into response with 200 response code for Quote API with "freightType": "PARCEL" & "shippingMethod": "STANDARD" | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 18/Jul/25 4:26 AM | 19/Aug/25 11:36 AM | Done | 25/Jul/25 5:17 AM | PFO Sprint 9 | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2110 | 209906 | [QA10][Delivery API] - "Validate" API response - incorrect sellableQty value from warehouse is shown | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 17/Jul/25 9:58 AM | 19/Aug/25 11:36 AM | Done | 07/Aug/25 8:24 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2094 | 209537 | [QA10][Delivery API] - POST "Update Schedule" API giving 200 response with Invalid Phone number | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | Done | Done | 16/Jul/25 9:50 AM | 27/Aug/25 10:39 AM | Done | 18/Aug/25 1:28 PM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2092 | 209483 | [QA10][Delivery API] - POST "Update Schedule" API giving 200 response with Invalid SKU | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 16/Jul/25 9:25 AM | 19/Aug/25 11:35 AM | Done | 25/Jul/25 2:31 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2087 | 209453 | [QA10][Delivery API] - For Invalid email format into payload getting 200 response with schedule ID for "Update Schedule" API even | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 16/Jul/25 8:22 AM | 19/Aug/25 11:35 AM | Done | 17/Jul/25 6:04 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2085 | 209441 | [QA10][Delivery API] - POST "Update schedule" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | CODE REVIEW | In Progress | 16/Jul/25 7:37 AM | 02/Sep/25 8:35 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2084 | 209439 | [QA10][Delivery API] - Getting 400 response with "LPTU_ERROR" for "Commit Schedule" API for valid payload request | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 16/Jul/25 7:19 AM | 19/Aug/25 11:35 AM | Done | 28/Jul/25 10:05 AM | PFO Sprint 10
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2060 | 208855 | [Ord][MS] Set Payment Method | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Olivia Lee / LG CNS | 712020:27824211-817d-4585-bce0-2d366d6880db | Low | READY FOR QA | In Progress | 14/Jul/25 10:45 PM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2050 | 208551 | [QA10][Delivery API] - Getting 400 Bad request response for Availability API with "freightType": "PARCEL" & "shippingMethod": "Next-Day" | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 14/Jul/25 8:48 AM | 19/Aug/25 11:35 AM | Done | 21/Jul/25 12:51 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2043 | 208533 | [QA10][Promo][MS]:Promotion Not Applied for Matching SKUs in No Coupon Scenario | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Monica Das / Marlabs | 712020:61bc7f75-c335-40fb-b325-b685a92814d3 | High | READY FOR STAGING | Done | 14/Jul/25 7:22 AM | 19/Aug/25 11:35 AM | Done | 17/Jul/25 3:31 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2042 | 208506 | [QA10][Delivery API] - POST "Commit Schedule" API giving 200 response with Invalid SKU | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 14/Jul/25 6:30 AM | 19/Aug/25 11:35 AM | Done | 21/Jul/25 12:51 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2037 | 208470 | [QA10][Delivery API] - POST "Commit Schedule" API in paload Schedule Date, Start & endtime parameter missing into payload | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | Done | Done | 14/Jul/25 2:49 AM | 19/Aug/25 11:37 AM | Done | 15/Jul/25 2:53 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2030 | 208251 | [QA10][Delivery API] - POST "Commit Schedule" API for null email id - error message into response is not proper | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Low | Done | Done | 11/Jul/25 10:39 AM | 19/Aug/25 11:37 AM | Done | 15/Jul/25 3:15 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2029 | 208232 | [QA10][Delivery API] - Getting 500 response for POST "Commit Schedule" API for valid payload request | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Blocker | READY FOR STAGING | Done | 11/Jul/25 9:51 AM | 19/Aug/25 11:37 AM | Done | 17/Jul/25 2:45 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2027 | 208208 | [QA10][Delivery API] - "Get Estimate" API for is giving additional data in response i.e. "totalEstimatedCost" which is not mentioned into TDD | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 11/Jul/25 9:14 AM | 25/Aug/25 2:24 AM | Done | 18/Aug/25 7:02 AM | PFO Sprint 11
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2014 | 207922 | [QA10][Delivery API] - "Get Estimate" API for is giving Incorrect Estimates date and Days for LMD freight type | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 10/Jul/25 8:47 AM | 19/Aug/25 11:36 AM | Done | 17/Jul/25 7:56 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-2012 | 207903 | [QA10][Delivery API] - "Get available slot" API is giving 400 response if we pass todays date into "firstAvailableDate" parameter | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 10/Jul/25 7:11 AM | 19/Aug/25 11:36 AM | Done | 18/Jul/25 9:51 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1995 | 207563 | [QA10][Promo][MS]:Discount applied for random SKU not present in rule condition list, Magento, or database for Rule ID 5624 | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Monica Das / Marlabs | 712020:61bc7f75-c335-40fb-b325-b685a92814d3 | Medium | READY FOR STAGING | Done | 09/Jul/25 8:47 AM | 19/Aug/25 11:35 AM | Done | 17/Jul/25 4:17 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1993 | 207555 | [QA10][Delivery API] - "Get slot" for Missing Auth token error message is not proper | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Low | Done | Done | 09/Jul/25 7:53 AM | 19/Aug/25 11:35 AM | Done | 15/Jul/25 3:17 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1991 | 207542 | [QA10][Delivery API] - "Validate" API for "Parcel" freight Type getting availability = false even if for next nearest warehouse stock is available | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 09/Jul/25 6:10 AM | 19/Aug/25 11:35 AM | Done | 22/Jul/25 3:07 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1984 | 207204 | [QA10][Delivery API] - "Validate" API is giving 200 response with warehouse details but for same SKU Next-day delivery is not given on FE | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 08/Jul/25 11:01 AM | 19/Aug/25 11:37 AM | Done | 18/Jul/25 10:44 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1982 | 207101 | [QA10][Delivery API] - "Validate" API for Incorrect Zipcode getting 404 with error message "WAREHOUSE_INVALID" | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 08/Jul/25 7:31 AM | 19/Aug/25 11:37 AM | Done | 17/Jul/25 9:13 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1980 | 207096 | [QA10][Delivery API] - "Validate" API for invalid/expired token giving 200 response with warehouse details | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | DEFERRED | Done | 08/Jul/25 6:43 AM | 19/Aug/25 11:37 AM | Done | 17/Jul/25 8:36 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1978 | 207087 | [QA10][Delivery API] - "Validate" API for blank Zipcode getting incorrect error message | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Low | Done | Done | 08/Jul/25 5:05 AM | 19/Aug/25 11:37 AM | Done | 15/Jul/25 3:18 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1976 | 207082 | [QA10][Delivery API] - "Validate" API for blank Freight type getting incorrect error message | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Low | Done | Done | 08/Jul/25 4:43 AM | 19/Aug/25 11:37 AM | Done | 15/Jul/25 3:19 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1973 | 207062 | [QA10][Delivery API] - "Validate" API is giving inproper error message as "MIXED_PRODUCT_ERP_TYPE_NOT_ALLOWED" | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 08/Jul/25 3:24 AM | 19/Aug/25 11:37 AM | Done | 17/Jul/25 9:17 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1961 | 206871 | [QA10][Delivery API] - Getting 404 response with wrong error message for "Get available slot" API if we pass invalid zipcode | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | READY FOR STAGING | Done | 07/Jul/25 8:36 AM | 19/Aug/25 11:36 AM | Done | 17/Jul/25 6:36 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1960 | 206864 | [QA10][Delivery API] - Getting 400 response for "Get available slot" API if we dont select optional parameter "firstAvailableDate" | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | High | READY FOR STAGING | Done | 07/Jul/25 7:58 AM | 19/Aug/25 11:36 AM | Done | 18/Jul/25 9:50 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1958 | 206859 | [QA10][Delivery API] - Availability/Validate API is showing Incorrect Message if we pass Invalid/Wrong/null Freight Type | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | Done | Done | 07/Jul/25 7:35 AM | 29/Aug/25 1:12 PM | Done | 25/Aug/25 3:20 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1928 | 206180 | [QA10][Delivery API] - Getting 400 response for "Commit Schedule" API for valid payload request | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 03/Jul/25 10:07 AM | 19/Aug/25 11:36 AM | Done | 17/Jul/25 2:44 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1923 | 206103 | [QA10][Delivery API] - Availability API is giving 404 frequently with valid payload | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 03/Jul/25 7:55 AM | 19/Aug/25 11:36 AM | Done | 16/Jul/25 7:59 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1922 | 206100 | [QA10][Delivery API] - Getting success response for Availability API with "freightType": "LMD" & "shippingMethod": "EXPEDITED" | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Critical | READY FOR STAGING | Done | 03/Jul/25 7:22 AM | 19/Aug/25 11:36 AM | Done | 18/Jul/25 10:48 AM | PFO Sprint 9
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1842 | 204397 | [QA10][Promo][MS]:Need Info-'last_used_at' field is not getting displayed in 'Coupons' table but it is coming from Magento in Rule Usage | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Medium | READY FOR STAGING | Done | 27/Jun/25 7:58 AM | 19/Aug/25 11:36 AM | Done | 22/Jul/25 6:08 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1837 | 204388 | [QA10][Promo][MS]: 'Last used at' value is being displayed as the 'updated_at' value in the 'rule_usage' table | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Medium | READY FOR STAGING | Done | 27/Jun/25 7:21 AM | 19/Aug/25 11:36 AM | Done | 22/Jul/25 7:03 AM | PFO Sprint 10
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1835 | 204385 | [MS] Send Individual Coupon data to CMS from MS while syncing Promotion | Shubham Malu / Encora | 6245a49ff3824d006a58a342 | Shubham Malu / Encora | 6245a49ff3824d006a58a342 | Low | Done | Done | 27/Jun/25 6:58 AM | 19/Aug/25 11:37 AM | Done | 25/Jul/25 3:55 AM | PFO Sprint 10
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1770 | 203566 | [BOPIS] Create a API to check availability for location store | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | CODE REVIEW | In Progress | 24/Jun/25 9:34 PM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1769 | 203324 | [BOPIS] Create a API to fetch location details based on provider and locationId | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | RETIRED | Done | 24/Jun/25 10:42 AM | 19/Aug/25 11:35 AM | Done | 30/Jun/25 8:41 AM | PFO Sprint 8
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1751 | 203245 | Handle Negative Scenario | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | Done | Done | 24/Jun/25 8:14 AM | 26/Aug/25 4:15 PM | Done | 26/Aug/25 4:15 PM | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1687 | 202353 | [QA10][Promo][MS]: 'is_mapped' field value is getting displayed as 0 in 'promotion_content_messages' table | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Medium | READY FOR STAGING | Done | 20/Jun/25 7:36 AM | 19/Aug/25 11:35 AM | Done | 22/Jul/25 6:50 AM | PFO Sprint 10
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1637 | 202056 | Create availability API | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | IN QA | In Progress | 19/Jun/25 8:30 AM | 08/Aug/25 1:10 PM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1571 | 200722 | [QA10][Promo][MS]: 'Channel' field value is getting displayed as Blank in 'coupon_usage' table | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Medium | READY FOR STAGING | Done | 13/Jun/25 5:04 AM | 19/Aug/25 11:36 AM | Done | 17/Jul/25 5:03 AM | PFO Sprint 9
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1233 | 196083 | [Product] [MS] Add column | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | Done | Done | 27/May/25 9:36 PM | 26/Aug/25 3:58 PM | Done | 26/Aug/25 3:58 PM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1213 | 195815 | [QA10][MS] - GET "Carrier warehouse" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 26/May/25 9:30 AM | 26/Aug/25 4:03 PM | Done | 26/Aug/25 4:03 PM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1211 | 195806 | [QA10][MS] - GET "Carrier Service Mapping" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 26/May/25 8:32 AM | 26/Aug/25 4:03 PM | Done | 26/Aug/25 4:03 PM | PFO Sprint 12
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1200 | 194893 | [talend] lg_vw_product_spec update column in talend for PDS service | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Siddharthsinh Rathod / Encora | 624b60f2f3824d006a5b5edd | Low | READY FOR STAGING | Done | 23/May/25 11:40 AM | 29/Aug/25 2:28 AM | Done | 03/Jun/25 9:30 AM | PFO Sprint 6
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1188 | 194231 | [QA10][MS] - POST "Draft Schedule" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 22/May/25 9:22 AM | 26/Aug/25 4:04 PM | Done | 26/Aug/25 4:04 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1180 | 194221 | [QA10][MS] - GET "Draft Schedule" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 22/May/25 8:36 AM | 26/Aug/25 4:04 PM | Done | 26/Aug/25 4:04 PM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1179 | 194206 | [QA10][MS] - GET " All Config" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 22/May/25 7:38 AM | 26/Aug/25 4:04 PM | Done | 26/Aug/25 4:04 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1177 | 194201 | [QA10][MS] - Need information : For Post config ticket/task is missing but in TDD POST "Add Config" method is mentioned | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | DEFERRED | Done | 22/May/25 7:02 AM | 01/Sep/25 10:49 PM | Done | 01/Sep/25 10:49 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1174 | 194101 | [QA10][MS] - GET " Warehouse Details" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 22/May/25 3:34 AM | 26/Aug/25 4:04 PM | Done | 26/Aug/25 4:04 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1156 | 193905 | [QA10][MS] - GET "Warehouse Details" API is giving "regionID" additional field into Response body which not into DB Tabel & not mentioned into TDD | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Medium | Done | Done | 21/May/25 9:47 AM | 19/Aug/25 11:36 AM | Done | 22/Jul/25 3:12 AM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1148 | 193811 | [QA10][MS] - GET " warehouse-leadtime" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 21/May/25 7:06 AM | 26/Aug/25 4:05 PM | Done | 26/Aug/25 4:05 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1143 | 193772 | [QA10][MS][Delivery] System Layer API - Get Postal Location By ZipCode : API performance time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Bibhishan Dhagate / Encora | 712020:c69ae79c-8e20-49c7-8644-aca5633d60a3 | Lowest | RETIRED | Done | 21/May/25 5:01 AM | 26/Aug/25 4:05 PM | Done | 26/Aug/25 4:05 PM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1141 | 193768 | [QA10][MS] - POST " commit schedule" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 21/May/25 4:14 AM | 26/Aug/25 4:05 PM | Done | 26/Aug/25 4:05 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1135 | 193704 | [Product Service] Create API to fetch Inventory | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | RE-OPENED | To Do | 20/May/25 9:23 PM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1129 | 193538 | [QA10][MS] - GET " commit schedule" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 20/May/25 9:13 AM | 26/Aug/25 4:05 PM | Done | 26/Aug/25 4:05 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1127 | 193525 | QA10 [Delivery-API] : Estimate API for PLP page is giving NULL data for LMD for few zipcodes (01001,96161,77027,44064) | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Akash Suryawanshi / Qualitest | 712020:c64b05e6-39f0-4401-8423-333d5b4d4dca | High | READY FOR STAGING | Done | 20/May/25 8:27 AM | 01/Sep/25 10:07 AM | Done | 01/Sep/25 10:07 AM | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-1094 | 193219 | [QA10][MS] - GET " National Holidays list" API response time is more than 500ms | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Lowest | RETIRED | Done | 19/May/25 6:32 AM | 26/Aug/25 4:06 PM | Done | 26/Aug/25 4:06 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-990 | 189746 | [QA][API] API returns 500 Internal Server Error when SKU ID is blank | Monica Das / Marlabs | 712020:61bc7f75-c335-40fb-b325-b685a92814d3 | Monica Das / Marlabs | 712020:61bc7f75-c335-40fb-b325-b685a92814d3 | High | READY FOR STAGING | Done | 12/May/25 7:27 AM | 19/Aug/25 11:36 AM | Done | 28/Jul/25 2:04 AM | PFO Sprint 10
Bug | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-984 | 189727 | [QA][API] Product Availability API returns 200 OK for invalid/wrong SKU and postal code, unlike BestBuy API | Monica Das / Marlabs | 712020:61bc7f75-c335-40fb-b325-b685a92814d3 | Monica Das / Marlabs | 712020:61bc7f75-c335-40fb-b325-b685a92814d3 | High | READY FOR STAGING | Done | 12/May/25 6:10 AM | 19/Aug/25 11:36 AM | Done | 29/Jul/25 10:55 AM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 10
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-520 | 175482 | DS System Service | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Suriya Kumar Sivasubramania / Marlabs | 712020:4e8ccdf0-08f7-408e-a47a-110eee9c0634 | Low | READY FOR STAGING | Done | 01/Apr/25 9:57 AM | 19/Aug/25 11:35 AM | Done | 22/Jul/25 3:17 AM | PFO Sprint 3 | PFO Sprint 9 | PFO Sprint 10
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-283 | 173013 | TMS System Service | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Suriya Kumar Sivasubramania / Marlabs | 712020:4e8ccdf0-08f7-408e-a47a-110eee9c0634 | Low | READY FOR QA | In Progress | 19/Mar/25 2:04 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 9 | PFO Sprint 13
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-281 | 173010 | LPTU System Service | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Suriya Kumar Sivasubramania / Marlabs | 712020:4e8ccdf0-08f7-408e-a47a-110eee9c0634 | Low | READY FOR STAGING | Done | 19/Mar/25 1:50 AM | 19/Aug/25 11:37 AM | Done | 03/Jun/25 10:04 PM | PFO Sprint 1 | PFO Sprint 3 | PFO Sprint 6
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-254 | 172561 | UPS Service | Muhammad Lukmanul Hakim / LG Sinarmas | 712020:c0c20164-eeae-4a9c-b907-4016fac5a475 | Suriya Kumar Sivasubramania / Marlabs | 712020:4e8ccdf0-08f7-408e-a47a-110eee9c0634 | Low | Done | Done | 17/Mar/25 11:09 AM | 19/Aug/25 11:36 AM | Done | 16/Jun/25 11:35 AM | PFO Sprint 7
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-111 | 171186 | [MS] Dynamic Scheduling - Update API | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | READY FOR STAGING | Done | 10/Mar/25 9:57 AM | 01/Sep/25 1:42 AM | Done | 01/Sep/25 1:42 AM | PFO Sprint 13
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-110 | 171184 | [MS] Dynamic Scheduling - Commit API | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | READY FOR STAGING | Done | 10/Mar/25 9:57 AM | 01/Aug/25 3:58 PM | Done | 30/Jul/25 9:18 AM | PFO Sprint 13
Subtask | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-107 | 171181 | [MS] Estimate api for PDP and cart/checkout page | Smeet Dhabarde / Encora | 712020:3e9bfecb-fa53-43f6-bd2d-73dfd2332843 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | IN QA | In Progress | 10/Mar/25 9:56 AM | 08/Aug/25 1:01 PM |  |  | PFO Sprint 13
Task | PFO | Purchasing Flow Optimization | software | Nixal | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 |  | PFO-105 | 171179 | Delivery Process Service | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Roshan Modi / Encora | 62ac9c3f4639000068d5e4f0 | Low | In Progress | In Progress | 10/Mar/25 9:54 AM | 02/Sep/25 7:21 AM |  |  | PFO Sprint 13