## 18 Sep 25
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 8 ~ 12 Sep 25 | 5 | 5 | 0 | 0 | 100% | 0 | N/A | 1 Subtask, and 4 Bugs already resolved
SF Automation 2025 | 4 ~ 10 Sep 25 | 9 | 8 | 0 | 0 | 88.89% | 0 | N/A | 8 task finish
SF Core Unit 2025 | 4 ~ 10 Sep 25 | 11 | 11 | 1 | 1 | 100% | 0.090909 | 100% | 9 tasks and 2 stories have been completed, and 1 bug has been fixed.
SF Process DX Team 2025 | 4 ~ 10 Sep 25 | 4 | 3 | 0 | 0 | 75% | 0 | N/A | Finish 3 task, 1 Task still in progress
SINGLEX Business Unit Testing Project | 4 ~ 10 Sep 25 | 26 | 25 | 0 | 0 | 96.15% | 0 | N/A | 25 SSR have completed testing, while 1 SSR is still inprogress testing due to prioritizing the completion of a hotfix ticket that needs to be deployed first.
KB Bank System Maintenance | 8 ~ 12 Sep 25 | 4 | 4 | 1 | 1 | 100% | 0.25 | 100% | 5 tasks have been completed by LGSM Team, and after this the Banking Team will do Testing. And 1 bug already fixed
[Bank Sinarmas] Provision of Card Management System Services | 8 ~ 12 Sep 25 | 11 | 10 | 0 | 0 | 90.91% | 0 | N/A | One complex defect is currently being resolved. It is not considered a blocker, with an estimated completion date of next week.
Total |  | 70 | 66 | 2 | 2 | 92.99% | 0.048701 | 100%

## 25 Sep 25
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 15 ~ 19 Sep 25 | 26 | 26 | 0 | 0 | 100% | 0 | N/A | Finish all request
SF Automation 2025 | 11 ~ 17 Sep 25 | 5 | 5 | 0 | 0 | 100% | 0 | N/A | Finish all request
SF Core Unit 2025 | 11 ~ 17 Sep 25 | 25 | 19 | 0 | 0 | 76% | 0 | N/A | There are some tasks that have more than 20 sub-tasks, which means their workload is quite large.
SF Manufacture DX Team 2025 | 11 ~ 17 Sep 25 | 2 | 2 | 0 | 0 | 100% | 0 | N/A | Finish all request
SF Process DX Team 2025 | 11 ~ 17 Sep 25 | 29 | 27 | 0 | 0 | 93.1% | 0 | N/A | 27 task already finish, no bug found.
SINGLEX Business Unit Testing Project | 15 ~ 19 Sep 25 | 24 | 24 | 4 | 4 | 100% | 0.16667 | 100% | 24 SSR ticket already finish, 4 defect found already created ticket and still fixing by developer
KB Bank System Maintenance | 15 ~ 19 Sep 25 | 15 | 10 | 0 | 0 | 66.67% | 0 | N/A | Several tasks in In Development status are due at the end of October 2025 because they have a large workload.
LGSM Career Job Portal | 15 ~ 19 Sep 25 | 33 | 33 | 0 | 0 | 100% | 0 | N/A | Resolved 17 bugs. Completed 8 user stories. Finished 8 sub-tasks.
[Bank Sinarmas] Provision of Card Management System Services | 15 ~ 19 Sep 25 | 159 | 170 | 0 | 0 | 106.9% | 0 | N/A | The plan was 159 tasks, but the team completed 170 because some tasks were finished faster than expected and a few priorities were accelerated. So the team slightly overachieved the target.
Total |  | 318 | 316 | 4 | 4 | 93.63% | 0.018519 | 100%

## Draft (hidden)
| Total Workload | 0
| Completed Workload | 0
| Averange Productivity Rate | 0%
| Project Name | Weekly Period | Total Workload | Completed Workload | Productivity Rate | Comment
Hakim | [LGUS] Purchasing Enhancement Project
Wirework | GDC Smart Factory - SF Automation 2025
Wirework | GDC Smart Factory - SF Core Unit 2025
Close | GDC SF Intelligent Unit Testing Project
Wirework | GDC Smart Factory - SF Manufacturing DX Team 2025
Wirework | GDC Smart Factory - SF Process DX Team 2025
Candra | GDC SINGLEX Business Unit Testing Project
Virza | Network Installation for New Tobacco Factory of KT&G
Andika | SHINE NGBS KB Bank System Maintenance
# | HLI
Andini | [Bank Sinarmas] Provision of Service of Card Management System
Wirework | GDC SF Solution Unit Quality DX Team Project 2025
Sapta | Job Portal
Victor | SMX01 Data Center MEP Project
Sabian | LG Ensol US System Maintenance Project

## Test (hidden)
Total Workload | 71
Completed Workload | -7
Averange Productivity Rate | -9.859%
Project Name | Period | Workload | Inprogress | Completed | Productivity Rate | Comment
[LGUS] Purchasing Enhancement Project | 8 - 12 September 2025 | 58 | 62 | -4 | -6.897%
GDC Smart Factory - SF Automation 2025 | 4 - 10 September 2025 | 62 | 54 | 8 | 12.9%
GDC Smart Factory - SF Core Unit 2025 | 4 - 10 September 2025 | 100 | 54 | 46 | 46%
GDC SF Intelligent Unit Testing Project | 4 - 10 September 2025 | 84 | 58 | 26 | 30.95%
GDC Smart Factory - SF Manufacturing DX Team 2025 | 8 - 12 September 2025 | 93 | 65 | 28 | 30.11%
GDC Smart Factory - SF Process DX Team 2025 | 8 - 12 September 2025 | 87 | 67 | 20 | 22.99%
GDC SINGLEX Business Unit Testing Project | 8 - 12 September 2025 | 76 | 76 | 0 | 0%
Network Installation for New Tobacco Factory of KT&G | 9 - 12 September 2025 | 71 | 78 | -7 | -9.859%
SHINE NGBS KB Bank System Maintenance | 10 - 12 September 2025 | 70 | 73 | -3 | -4.286%
HLI | 11 - 12 September 2025 | 53 | 54 | -1 | -1.887%
[Bank Sinarmas] Provision of Service of Card Management System | 12 - 12 September 2025 | 58 | 64 | -6 | -10.34%
GDC SF Solution Unit Quality DX Team Project 2025 | 13 - 12 September 2025 | 77 | 75 | 2 | 2.597%
Job Portal | 14 - 12 September 2025 | 55 | 65 | -10 | -18.18%
SMX01 Data Center MEP Project | 15 - 12 September 2025 | 72 | 75 | -3 | -4.167%
LG Ensol US System Maintenance Project | 16 - 12 September 2025 | 57 | 77 | -20 | -35.09%

## 02 Oct 25
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 22 - 26 Sep 2025 | 2 | 2 | 0 | 0 | 100% | 0 | N/A | All assigned workload has been completed.
SF Automation 2025 | 18 - 24 Sep 2025 | 5 | 5 | 0 | 0 | 100% | 0 | N/A | All assigned workload has been completed.
SF Core Unit 2025 | 18 - 24 Sep 2025 | 27 | 26 | 2 | 2 | 96.3% | 0.076923 | 100% | Finish 7 Story, 20 task , and 2 defect already fixed
SF Manufacture DX Team 2025 | 18 - 24 Sep 2025 | 3 | 3 | 0 | 0 | 100% | 0 | N/A | All assigned workload has been completed.
SF Process DX Team 2025 | 18 - 24 Sep 2025 | 16 | 16 | 0 | 0 | 100% | 0 | N/A | All assigned workload has been completed.
SINGLEX Business Unit Testing Project | 22 - 26 Sep 2025 | 27 | 27 | 2 | 2 | 100% | 0.074074 | 100% | 27 SSR testing ticket already finish, 2 defect found already created ticket.
KB Bank System Maintenance | 22 - 26 Sep 2025 | 26 | 25 | 3 | 3 | 96.15% | 0.12 | 100% | 1 ticket In Development status and resolved 3 bugs.
LGSM Career Job Portal | 22 - 26 Sep 2025 | 13 | 13 | 5 | 5 | 100% | 0.38462 | 100% | Resolved 5 bugs. Completed 3 user stories. Finished 1 task and 4 sub-tasks.
[Bank Sinarmas] Provision of Card Management System Services | 22 - 26 Sep 2025 | 160 | 197 | 0 | 0 | 123.1% | 0 | N/A | Exceeded the target
Total |  | 279 | 314 | 12 | 12 | 101.7% | 0.072846 | 100%

## Draft V.2 (hidden)
Total Workload | 54
Completed Workload | 72
Averange Productivity Rate | 137.1%
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 22 - 26 September 2025 | 5 | 10 | 24 | 4 | 200% | 2.4 | 16.67%
SF Automation 2025 | 18 - 24 September 2025 | 10 | 9 | 54 | 73 | 90% | 6 | 135.2%
SF Core Unit 2025 | 18 - 24 September 2025 | 7 | 7 | 74 | 92 | 100% | 10.5714 | 124.3%
SF Manufacture DX Team 2025 | 18 - 24 September 2025 | 10 | 9 | 26 | 13 | 90% | 2.8889 | 50%
SF Process DX Team 2025 | 18 - 24 September 2025 | 4 | 9 | 7 | 22 | 225% | 0.77778 | 314.3%
SINGLEX Business Unit Testing Project | 22 - 26 September 2025 | 7 | 7 | 45 | 61 | 100% | 6.4286 | 135.6%
KB Bank System Maintenance | 22 - 26 September 2025 | 2 | 10 | 26 | 87 | 500% | 2.6 | 334.6%
LGSM Career Job Portal | 22 - 26 September 2025 | 7 | 5 | 67 | 59 | 71.43% | 13.4 | 88.06%
Bank Sinarmas Project | 22 - 26 September 2025 | 2 | 6 | 60 | 21 | 300% | 10 | 35%
Total |  | 54 | 72 | 383 | 432 | 186.3% | 611.9% | 137.1%

## 09 Oct 25
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 29 Sep ~ 3 Oct 2025 | 16 | 14 | 1 | 1 | 87.5% | 0.071429 | 100% | finish 14 task and solved 1 bug, 2 task still in progress
SF Automation 2025 | 25 Sep ~ 1 Oct 2025 | 19 | 19 | 0 | 0 | 100% | 0 | N/A | finish 2 story and 17 task
SF Core Unit 2025 | 25 Sep ~ 1 Oct 2025 | 45 | 36 | 0 | 0 | 80% | 0 | N/A | finish 34 task and 2 story, and 9 are still in progress because each task has a heavy workload - some include more than 30 sub-tasks.
SF Manufacture DX Team 2025 | 25 Sep ~ 1 Oct 2025 | 1 | 1 | 0 | 0 | 100% | 0 | N/A | All assigned workload has been completed.
SF Process DX Team 2025 | 25 Sep ~ 1 Oct 2025 | 27 | 27 | 0 | 0 | 100% | 0 | N/A | finish 21 task and 6 story
SINGLEX Business Unit Testing Project | 29 Sep ~ 3 Oct 2025 | 38 | 34 | 1 | 1 | 89.47% | 0.029412 | 100% | 34 SSR ticket already finish and 4 ticket still in testing. 1 defect found and already created ticket.
KB Bank System Maintenance | 29 Sep ~ 3 Oct 2025 | 23 | 22 | 1 | 1 | 95.65% | 0.045455 | 100% | 1 task in In Development status has a large workload.
LGSM Career Job Portal | 29 Sep ~ 3 Oct 2025 | 7 | 7 | 4 | 4 | 100% | 0.57143 | 100% | Resolved 4 bugs. Completed 2 user stories. Finished 1 sub-tasks.
[Bank Sinarmas] Provision of Card Management System Services | 26 Sep ~ 2 Oct 2025 | 215 | 241 | 0 | 0 | 112.1% | 0 | N/A | [Cumulative]- Authorization/Common part : Plan = 72 ¦ Actual = 77- Front part : Plan = 70 ¦ Actual = 92- Back-end part : Plan = 73 ¦ Actual = 72 (There was a delay in reflecting the brand incoming file due to work reference checks)Overall Progress = 37.8%
Total |  | 391 | 401 | 7 | 7 | 96.08% | 0.079747 | 100%

## 16 Oct 25
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 6 Oct ~ 10 Oct 2025 | 26 | 26 | 0 | 0 | 100% | 0 | N/A | Finish 7 Task and resolved 19 defect
SF Automation 2025 | 2 Oct ~ 8 Oct 2025 | 22 | 22 | 0 | 0 | 100% | 0 | N/A | Finish 3 story and 19 task, no defect found
SF Core Unit 2025 | 2 Oct ~ 8 Oct 2025 | 132 | 132 | 1 | 1 | 100% | 0.0075758 | 100% | Finish 105 Story, 27 task and solved 1 defect
SF Manufacture DX Team 2025 | 2 Oct ~ 8 Oct 2025 | 1 | 1 | 0 | 0 | 100% | 0 | N/A | Finish [RMS] Simulating Validation from RMS Simulator
SF Process DX Team 2025 | 2 Oct ~ 8 Oct 2025 | 52 | 42 | 0 | 0 | 80.77% | 0 | N/A | Finish 21 Story, 21 task 10 task still in progress
SINGLEX Business Unit Testing Project | 6 Oct ~ 10 Oct 2025 | 8 | 8 | 1 | 1 | 100% | 0.125 | 100% | 8 SSR tickets have been completed, 1 defect has been reported. Notes: The number of tickets is lower this week due to the long holiday in Korea.
KB Bank System Maintenance | 6 Oct ~ 10 Oct 2025 | 37 | 36 | 4 | 4 | 97.3% | 0.11111 | 100% | Finish 36 Task, 1 task in In Development status, resolved 4 defect.
LGSM Career Job Portal | 6 Oct ~ 10 Oct 2025 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | The team is on standby, waiting for HR’s final requirements to start the next phase.
[Bank Sinarmas] Provision of Card Management System Services | 3 Oct ~ 9 Oct 2025 | 238 | 256 | 0 | 0 | 107.6% | 0 | N/A | [Cumulative] - Authorization/Common part : Plan = 76 ¦ Actual = 83 - Front part : Plan = 89 ¦ Actual = 92 - Back-end part : Plan = 73 ¦ Actual = 81 Overall Progress = 37.8%
Total |  | 516 | 523 | 6 | 6 | 98.2% | 0.030461 | 100%

## 23 Oct 25
Project Name | Period | Total Workload (Planned) | Completed Workload (Actual) | Defect Found | Defect Fixed | Productivity Rate | Defect Density | Defect Correction Rate | Issue/ Risk/ Note
Purchasing Enhancement Project | 13 ~ 17 Oct 2025 | 10 | 10 | 0 | 0 | 100% | 0 | N/A | Finish 2 task and resolved 8 defect
SF Automation 2025 | 9 ~ 15 Oct 2025 | 19 | 17 | 0 | 0 | 89.47% | 0 | N/A | Finish 16 Task and 1 Story, 2 Task still in progress
SF Core Unit 2025 | 9 ~ 15 Oct 2025 | 132 | 128 | 1 | 1 | 96.97% | 0.0078125 | 100% | Finish 105 Story, 23 Task. 1 defect already resolved
SF Manufacture DX Team 2025 | 9 ~ 15 Oct 2025 | 1 | 1 | 0 | 0 | 100% | 0 | N/A | Finish Manual - EIF Validation Simulation using RMS Simulator
SF Process DX Team 2025 | 9 ~ 15 Oct 2025 | 12 | 8 | 0 | 0 | 66.67% | 0 | N/A | Finish 8 task and 4 story still in progress but due date 31-10-2025
SINGLEX Business Unit Testing Project | 13 ~ 17 Oct 2025 | 35 | 35 | 0 | 0 | 100% | 0 | N/A | Finish 3 story and 19 task, no defect found
KB Bank System Maintenance | 13 ~ 17 Oct 2025 | 15 | 12 | 1 | 1 | 80% | 0.083333 | 100% | 3 tasks In Development status are due at 31 October 2025
LGSM Career Job Portal | 13 ~ 17 Oct 2025 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | We received the initial requirements from HR (Wilson) and held a kick-off meeting to align on scope. User stories have been drafted and will be reviewed before design approval. Development is expected to start in early November.
[Bank Sinarmas] Provision of Card Management System Services | 10 ~ 16 Oct 2025 | 255 | 297 | 0 | 0 | 116.5% | 0 | N/A | [Cumulative] - Authorization/Common part : Plan = 81 ¦ Actual = 91 - Front part : Plan = 91 ¦ Actual = 111 - Back-end part : Plan = 83 ¦ Actual = 95 Overall Progress = 46.8%
Total |  | 479 | 508 | 2 | 2 | 93.7% | 0.011393 | 100%