## SI
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Sprint | Sprint Schedule | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 13 | SI | S#1 | 2025-03-03 - 2025-03-26 | 34 | 34 | 21 | 21 | 100% | 0.61765 | 100% | All 34 tasks were completed. 21 defects were found and all were fixed.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 13 | SI | S#2 | 2025-04-08 - 2025-05-02 | 21 | 21 | 8 | 8 | 100% | 0.38095 | 100% | Finished all 21 tasks. 8 defects were reported and resolved.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 13 | SI | S#3 | 2025-05-05 - 2025-06-25 | 48 | 48 | 10 | 10 | 100% | 0.20833 | 100% | 48 tasks were done with no delays. 10 defects appeared and were handled.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 13 | SI | S#4 | 2025-06-02 - 2025-07-02 | 38 | 38 | 22 | 22 | 100% | 0.57895 | 100% | Completed all 38 tasks. 22 defects showed up and were successfully fixed.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | 13 | SI | S#1 | 2025-01-13 - 2025-02-10 | 128 | 70 | 6 | 6 | 54.69% | 0.085714 | 100% | 70 out of 128 tasks were completed, with 6 defects reported and all 6 successfully fixed. 7 Canceled Ticket
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | 13 | SI | S#2 | 2025-02-10 - 2025-03-10 | 110 | 71 | 4 | 4 | 64.55% | 0.056338 | 100% | Completed 71 out of 110 tasks. 4 defects appeared and were all resolved.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | 13 | SI | S#3 | 2025-03-11 - 2025-04-08 | 53 | 37 | 3 | 3 | 69.81% | 0.081081 | 100% | 37 tasks finished from 53. 3 defects showed up and got fixed.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | 13 | SI | S#4 | 2025-04-09 - 2025-05-07 | 75 | 35 | 22 | 22 | 46.67% | 0.62857 | 100% | Only 35 of 75 tasks were done. 22 defects found, all were fixed.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | 13 | SI | S#5 | 2025-05-08 - 2025-06-05 | 52 | 48 | 5 | 5 | 92.31% | 0.10417 | 100% | 48 out of 52 tasks were completed. 5 defects came up and were handled.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | 13 | SI | S#6 | 2025-06-09 - 2025-07-07 | 83 | 26 | 17 | 14 | 31.33% | 0.65385 | 82.35% | Just 26 of 83 tasks were finished. 17 defects found, 14 were fixed.
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Testers | SI | S#1 | 2025-04-21 - 2025-04-25 | 265 | 265 | 0 | 0 | 100% | 0 | #DIV/0! | Sprint #1 - Testing Scenario: Scenario received on May 25, completed on June 25 Total scenarios: 269 Executed: 265 In Progress: 0 Passed: 222 Failed: 41 For the 41 defects found by the testers, there has been no feedback from the Korean Team so far regarding when the retest will be conducted.

## January
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 8 | 7 | 0 | 0 | 87.5% | 0 | #DIV/0! | 7 out of 8 tasks were completed, with no defects reported.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | SF Automation 2025 is not yet fully using Wire-Work for Task Tracking Management
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 2 | 2 | 0 | 0 | 100% | 0 | #DIV/0! | SF Core is not yet fully using Wire-Work for Task Tracking Management
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | All 14 tasks were completed without any defect occurrences.

## February
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 8 | 7 | 0 | 0 | 87.5% | 0 | #DIV/0! | 7 out of 8 tasks were completed, with no defects reported.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 4 | 4 | 0 | 0 | 100% | 0 | #DIV/0! | The single assigned task was completed successfully, with no defects identified.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 24 | 24 | 0 | 0 | 100% | 0 | #DIV/0! | All 24 tasks were completed with no defects reported.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 69 | 69 | 0 | 0 | 100% | 0 | #DIV/0! | All 69 tasks were successfully completed without any defect occurrence. Cancel : 3

## March
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 6 | 5 | 0 | 0 | 83.33% | 0 | #DIV/0! | 5 out of 6 tasks were completed, with no defects reported.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 30 | 30 | 0 | 0 | 100% | 0 | #DIV/0! | All 30 tasks were successfully completed without any defects.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 105 | 99 | 0 | 0 | 94.29% | 0 | #DIV/0! | Cancel ticket : 6 In Checking : 3 In Progress : 2 Todo : 1
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 32 | 31 | 0 | 0 | 96.88% | 0 | #DIV/0! | 31 out of 32 tasks were completed with zero defects reported. 1 checking subtasks SSMPP002-550

## April
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 9 | 8 | 0 | 0 | 88.89% | 0 | #DIV/0! | 8 out of 9 tasks were completed, with no defects reported.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 17 | 17 | 0 | 0 | 100% | 0 | #DIV/0! | All 17 tasks were completed successfully with zero defects identified.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 94 | 94 | 0 | 0 | 100% | 0 | #DIV/0! | All 94 tasks were completed with no defects detected.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 63 | 61 | 0 | 0 | 96.83% | 0 | #DIV/0! | 61 of the 63 planned tasks were completed, and no defects were reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 16 | 16 | 0 | 0 | 100% | 0 | #DIV/0! | All 16 tasks were delivered without any defect occurrence.

## May
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 10 | 10 | 0 | 0 | 100% | 0 | #DIV/0! | All 10 tasks were completed successfully with no defects reported.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 42 | 42 | 0 | 0 | 100% | 0 | #DIV/0! | All 42 tasks were completed, and no defects were detected.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 42 | 42 | 1 | 1 | 100% | 0.02381 | 100% | All 42 tasks were delivered with no defects identified.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 50 | 50 | 0 | 0 | 100% | 0 | #DIV/0! | All 50 tasks were completed without any defect occurrences, canceled : 5
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 37 | 37 | 0 | 0 | 100% | 0 | #DIV/0! | All 37 tasks were completed. No defects have been reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 119 | 119 | 12 | 12 | 100% | 0.10084 | 100% | All 119 tasks were completed. A total of 12 defects were identified and fully resolved.

## June
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 13 | 11 | 0 | 0 | 84.62% | 0 | #DIV/0! | All 13 tasks were completed successfully with no defects reported.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 32 | 32 | 28 | 28 | 100% | 0.875 | 100% | All 32 tasks were completed, and 28 reported defects were fully resolved.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 57 | 57 | 0 | 0 | 100% | 0 | #DIV/0! | The project delivered all 57 tasks with no defects identified during execution.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 172 | 169 | 2 | 1 | 98.26% | 0.011834 | 50% | Out of 172 planned tasks, 169 were completed. Two defects were identified - one has already been fixed. Cancelled: 2 tasks Defect in progress: SSMPP002-1412
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 26 | 26 | 0 | 0 | 100% | 0 | #DIV/0! | All 26 completed. No defects have been reported, canceled 7
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 9 | 9 | 0 | 0 | 100% | 0 | #DIV/0! | All 9 tasks were completed without any defects identified.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 154 | 154 | 23 | 21 | 100% | 0.14935 | 91.3% | The project successfully completed all 154 tasks. 23 defects were reported and 21 has fixed

## July
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 148 | 143 | 7 | 6 | 96.62% | 0.048951 | 85.71%
| KB Bank System Maintenance | [LDC] SHINE NGBS |  |  |  | 9 | SM |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!

## Quality Metrics
Project evaluation will be conducted based on comprehensive "Project Quality Metrics," with the update frequency and evaluation approach tailored to the project type:
SI | For SI (System Implementation) projects, which involve building a new system from scratch, evaluations will be updated after every sprint to closely monitor development progress, quality, and issue resolution during incremental delivery phases.
SM | For SM (System Maintenance) projects, focused on maintaining and improving existing systems, evaluations will be updated monthly, allowing a broader view of ongoing system health and maintenance activities over time.
Quality Metrics
Indicator | Function Fulfilment Rate | Quality Rate
| Function Fulfilment Evaluation | Bug Density | Bug Correction Rate
Risk | Completed requests ≤ 70% | Bug density ≥ 3 or Bug correction rate ≤ 70%
Issue | Completed requests ≥ 70% and < 80% | Bug density ≥ 2 or Bug correction rate > 70% and ≤ 80%
Standard | Completed requests ≥ 80% | Bug density < 2 or Bug correction rate > 80%
Metric Definitions and Impact on Project Types
Functional Fulfillment: | Measures how much of the requested functions have been completed relative to the total planned functions for the project or component.
Bug Density | Number of bugs found relative to the size of the project/component - critical for both new development (SI) and ongoing maintenance (SM).
Bug Correction Rate: | Percentage of bugs fixed within the evaluated period, indicating responsiveness and maintenance quality.

## Project Kickoff Status
STATUS PROJECT KICK-OFF IN June.2025
IDB |  | May | June | Rate Kick-off | Highlight
Project | Plan
Actual
Pending
Project Name
Example
|  | Apr | May | Rate Kick-off | Highlight
SI/SM Group | Plan | 11 | 6 | 66.67% | 02 Project can't start as planned because the person is unavailable, detailed: + From April: R&D- LGES PLM project: Member of this project join VNB at 26. May---> QA guide & follow member project hold Kick-off as soon as possible + May: LG CNS Internal system Project (Total MM: 69)
| Actual | 10 | 4
| Pending | 1 | 2
| Project Name |  | 1. Smart logistic (DD) 2. LGE PCC (CX) 3. SOHO Opening AS Process (TEL) 4. LGIT Mexico Vehicle LS GMES Construction (SF)
CoE Group | Plan | 9 | 6 | 66.67% | 02 Project can't start as planned because the person is unavailable, detailed: SCMable, DevOnn AIDD 5 project remaining on April is now dropped (from E/S CoE Team)
| Actual | 1 | 4
| Pending | 8 | 2
| Project Name | 1.Butter fly | 1. Korean App 2. Olero 3. Singlex Data Hub 4. Singlex UAS