## SI
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Sprint | Sprint Schedule | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#1 | 2025-03-03 ~ 2025-03-26 | 10 | 10 | 21 | 21 | 100% | 2.1 | 100% | 16 out of 18 tasks have been completed successfully. All 16 identified defects have been resolved.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#2 | 2025-04-08 ~ 2025-05-02 | 8 | 8 | 8 | 8 | 100% | 1 | 100% | All tasks (11) have been completed. 6 defects were detected and have been fully fixed.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#3 | 2025-05-05 ~ 2025-06-25 | 20 | 18 | 12 | 10 | 90% | 0.66667 | 83.33% | 2 Tasks and 2 Issues are carried over and completed on Sprint 4
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#4 | 2025-06-02 ~ 2025-07-02 | 20 | 16 | 22 | 22 | 80% | 1.375 | 100% | 4 Tasks are carried over to Sprint 5. (3 completed, 1 carried over again to Sprint 6)
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#5 | 2025-07-02 ~ 2025-08-01 | 27 | 17 | 28 | 24 | 62.96% | 1.6471 | 85.71% | 10 Tasks and 4 Bugs are carried over to Sprint 6
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | SF Dev | SI | S#1 | 2025-01-13 ~ 2025-02-10 | 18 | 16 | 16 | 16 | 88.89% | 1 | 100% | 16 of 18 tasks completed. All 16 bugs detected have been fixed.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | SF Dev | SI | S#2 | 2025-02-10 ~ 2025-03-10 | 46 | 34 | 4 | 4 | 73.91% | 0.11765 | 100% | 34 out of 46 tasks done. 4 issues found and fixed.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | SF Dev | SI | S#3 | 2025-03-11 ~ 2025-04-08 | 24 | 21 | 3 | 3 | 87.5% | 0.14286 | 100% | Sprint completed with 21 of 24 tasks. All 3 defects resolved.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | SF Dev | SI | S#4 | 2025-04-09 ~ 2025-05-07 | 24 | 20 | 22 | 21 | 83.33% | 1.1 | 95.45% | 20 out of 24 tasks completed. 22 bugs found, with 21 already fixed.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | SF Dev | SI | S#5 | 2025-05-08 ~ 2025-06-05 | 27 | 23 | 5 | 5 | 85.19% | 0.21739 | 100% | Sprint achieved 85% task delivery. All 5 reported issues resolved.
| LGSM Sandbox | [LGSM] Internal Project |  |  | Ninan Kara Gicha Nasution | SF Dev | SI | S#6 | 2025-06-09 ~ 2025-07-07 | 28 | 20 | 17 | 14 | 71.43% | 0.85 | 82.35% | 20 of 28 tasks done. Out of 17 found bugs, 14 have been fixed so far.
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#1 | 2025-04-21 ~ 2025-04-25 | 265 | 265 | 0 | 0 | 100% | 0 | #DIV/0! | Sprint #1 - Testing Scenario: Scenario received on May 25, completed on June 25 Total scenarios: 269 Executed: 265 In Progress: 0 Passed: 222 Failed: 41

## January
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 8 | 7 | 0 | 0 | 87.5% | 0 | #DIV/0! | 7 out of 8 tasks were completed, with no defects reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 2 | 2 | 0 | 0 | 100% | 0 | #DIV/0! | SF Core is not yet fully using Wire-Work for Task Tracking Management
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | All 14 tasks were completed without any defect occurrences.

## February
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 8 | 7 | 0 | 0 | 87.5% | 0 | #DIV/0! | 7 of 8 tasks have been completed. No defects were found during this sprint.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 3 | 3 | 0 | 0 | 100% | 0 | #DIV/0! | All assigned tasks were completed successfully with zero defects reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 8 | 8 | 0 | 0 | 100% | 0 | #DIV/0! | Full task completion achieved with no bugs identified.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | 100% workload completed with clean execution and no defects recorded.

## March
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 6 | 5 | 0 | 0 | 83.33% | 0 | #DIV/0! | 5 out of 6 tasks were completed, showing solid progress with no defects reported.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 24 | 24 | 0 | 0 | 100% | 0 | #DIV/0! | 100% task completion (24/24). No defects found.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 19 | 18 | 0 | 0 | 94.74% | 0 | #DIV/0! | 18 of 19 tasks completed. All with zero defects.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 7 | 7 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks completed (7/7).

## April
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 9 | 8 | 0 | 0 | 88.89% | 0 | #DIV/0! | 8 of 9 tasks completed. Smooth progress with no defects.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 14 | 14 | 0 | 0 | 100% | 0 | #DIV/0! | 100% completion. No issues encountered.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 28 | 28 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks delivered successfully.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 57 | 57 | 0 | 0 | 100% | 0 | #DIV/0! | No defects across all 57 tasks.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 16 | 16 | 0 | 0 | 100% | 0 | #DIV/0! | Full task completion. Testing went flawlessly.

## May
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 10 | 10 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks were completed successfully without any defects reported.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 42 | 42 | 0 | 0 | 100% | 0 | #DIV/0! | Project achieved full delivery with no quality issues encountered.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 7 | 7 | 1 | 1 | 100% | 0.14286 | 100% | All tasks delivered, with 1 defect discovered and promptly resolved.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 18 | 18 | 0 | 0 | 100% | 0 | #DIV/0! | Project completed without any technical issues or defects.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 37 | 37 | 0 | 0 | 100% | 0 | #DIV/0! | The sprint ended with 100% completion and no bugs recorded.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 119 | 119 | 0 | 0 | 100% | 0 | #DIV/0! | 119 task completed with 12 defects identified

## June
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 13 | 11 | 0 | 0 | 84.62% | 0 | #DIV/0! | 11 out of 13 tasks were completed. No defects were reported.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 60 | 60 | 0 | 0 | 100% | 0 | #DIV/0! | All tasks completed successfully. 28 defects resolved during the sprint.
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 13 | 13 | 0 | 0 | 100% | 0 | #DIV/0! | Project completed with full delivery and no issues encountered.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 50 | 49 | 1 | 1 | 98% | 0.020408 | 100% | Nearly all tasks were finished. 1 defect was identified and fixed.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 26 | 26 | 0 | 0 | 100% | 0 | #DIV/0! | 100% completion with no defects.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 5 | 5 | 0 | 0 | 100% | 0 | #DIV/0! | All 5 tasks completed. No issues encountered.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 154 | 154 | 0 | 0 | 100% | 0 | #DIV/0! | High workload accomplished. 23 defects were reported.

## July
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| Salesforce Maintenance & Enhancement Project | [GDC] LGUS | 2025-01-01 | 2025-08-31 | Nisha Devadas Bhat | 3 | SM | 11 | 9 | 2 | 2 | 81.82% | 0.22222 | 100% | 9 out of 11 tasks were completed. 2 defects were reported and all fixed.
| Purchasing Enhancement Project | [GDC] LGUS | 2025-04-16 | 2025-09-30 | Muhammad Lukmanul Hakim | 1 | SM | 83 | 82 | 0 | 0 | 98.8% | 0 | #DIV/0! | 82 out of 83 tasks were completed, mostly do defect fixing
| SF Automation 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Jeremy Marvin Christian | 11 | SM | 5 | 5 | 0 | 0 | 100% | 0 | #DIV/0! | All 5 tasks were completed. No defects were reported.
| SF Core Unit 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Stefanus Kurniawan, Willy Candra Sugianto | 39 | SM | 193 | 185 | 20 | 20 | 95.85% | 0.10811 | 100% | 185 out of 193 tasks were completed. 20 defects were reported and all fixed.
| SF Process DX Team 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-12-31 | Ninan Kara Gicha Nasution | 16 | SM | 58 | 58 | 0 | 0 | 100% | 0 | #DIV/0! | All 58 tasks were completed. No defects were reported.
| Solution Unit Quality DX Team Project 2025 | [GDC] Smart Factory | 2025-01-01 | 2025-06-30 | Ninan Kara Gicha Nasution | 3 | SM | 14 | 13 | 0 | 0 | 92.86% | 0 | #DIV/0! | 13 out of 14 tasks were completed. No defects were reported.
| SINGLEX Business Unit Testing Project | [GDC] SINGLEX | 2025-01-01 | 2025-12-31 | Riski Candra Aristiawan | 6 | SM | 148 | 143 | 0 | 0 | 96.62% | 0 | #DIV/0! | 143 out of 148 tasks were completed. 7 defects were reported
| KB Bank System Maintenance | [GDC] SHINE NGBS |  |  | Andhika Putra | 9 | SM | 44 | 40 | 1 | 1 | 90.91% | 0.025 | 100% | 40 out of 44 tasks were completed. 1 defect was reported and fixed.

## Quality Metrics
Project evaluation will be conducted based on comprehensive "Project Quality Metrics," with the update frequency and evaluation approach tailored to the project type:
SI | For SI (System Implementation) projects, which involve building a new system from scratch, evaluations will be updated after every sprint to closely monitor development progress, quality, and issue resolution during incremental delivery phases.
SM | For SM (System Maintenance) projects, focused on maintaining and improving existing systems, evaluations will be updated monthly, allowing a broader view of ongoing system health and maintenance activities over time.
Quality Metrics
Indicator | Function Fulfilment Rate | Quality Rate
| Function Fulfilment Evaluation | Bug Density | Bug Correction Rate
Risk | Completed requests ≤ 70% | Bug density ≥ 3 or Bug correction rate ≤ 70%
Issue | Completed requests ≥ 70% and < 80% | Bug density ≥ 2 or Bug correction rate > 70% and ≤ 80%
Standard | Completed requests ≥ 80% | Bug density < 2 or Bug correction rate > 80%
Metric Definitions and Impact on Project Types
Functional Fulfillment: | Measures how much of the requested functions have been completed relative to the total planned functions for the project or component.
Bug Density | Number of bugs found relative to the size of the project/component - critical for both new development (SI) and ongoing maintenance (SM).
Bug Correction Rate: | Percentage of bugs fixed within the evaluated period, indicating responsiveness and maintenance quality.