## Job Portal
Request Number | System | Type | Summary | Status | Sprint | Request Date | Start Date | Completion Date
GDC Request Number |  | Type | Type | Status | Status | Request Date | Start Date | Completing tasks
SSMPP003-445 | Job Portal | Bug | There is no notification email to requestor through email When "Hired" count = "People Required" | Closed | Sprint 6 | 2025-07-23 18:32 |  | 2025-08-29 15:54
SSMPP003-451 | Job Portal | Bug | The position of required skill and applicant's skill is reverse | Closed | Sprint 6 | 2025-07-25 18:14 |  | 2025-08-29 15:54
SSMPP003-452 | Job Portal | Bug | Required language is not displayed when doesn't match with applicant's language | Closed | Sprint 6 | 2025-07-25 18:25 |  | 2025-08-29 15:54
SSMPP003-462 | Job Portal | Bug | There is an error "There are incomplete fields. Applicant Count" when publish job posting | Closed | Sprint 6 | 2025-07-30 18:30 |  | 2025-08-29 15:54
SSMPP003-467 | Job Portal | Bug | There is an error "There are incomplete fields: Head Count" when HR want to approve a job request | Closed | Sprint 6 | 2025-08-05 12:52 |  | 2025-08-18 15:58
SSMPP003-468 | Job Portal | Bug | Requisition Reject/Approve Notes can be submitted without notes | Closed | Sprint 6 | 2025-08-05 13:05 |  | 2025-08-18 15:58
SSMPP003-474 | Job Portal | Bug | At Job Posting List and Detail. Hide Edit Button when user login is not the Creator | Closed | Sprint 6 | 2025-08-08 11:37 |  | 2025-08-29 15:54
SSMPP003-475 | Job Portal | Bug | [FE] At Job Detail. Show Publish Button when the user login is the creator | Closed | Sprint 6 | 2025-08-08 11:38 |  | 2025-08-29 15:54
SSMPP003-476 | Job Portal | Bug | [FE] At Job Posting. Hiring manager only can see Job List and Job Detail | Closed | Sprint 6 | 2025-08-08 11:38 |  | 2025-08-29 15:54
SSMPP003-419 | Job Portal | Test | Verify the Applicant on Application Details | Done | Sprint 6 | 2025-07-14 12:31 |  | 2025-08-19 17:18
SSMPP003-420 | Job Portal | Test | Verify Update Applicant Statuses | Done | Sprint 6 | 2025-07-14 15:17 |  | 2025-08-11 18:53
SSMPP003-477 | Job Portal | Bug | [FE] Refine Actions Button. It could be in Job Posting, Applicant Management, or in Job Requesition | Closed | Sprint 6 | 2025-08-08 11:50 |  | 2025-08-29 15:54
SSMPP003-478 | Job Portal | Bug | [FE] At Job Posting Detail. Publish Button didin't work. Allow headCount to be nullable | Closed | Sprint 6 | 2025-08-08 12:09 |  | 2025-08-29 15:54
SSMPP003-479 | Job Portal | Bug | Error Resume Loading in Applicant Management | Closed | Sprint 6 | 2025-08-11 18:38 |  | 2025-08-29 15:54
SSMPP003-480 | Job Portal | Bug | Status of 'Test Result' still in 'Test Code' instead of Test Code Description | Closed | Sprint 6 | 2025-08-11 18:39 |  | 2025-08-29 15:54
SSMPP003-490 | Job Portal | Bug | HR Notes is not recorded/ doesn't appears in Job Posting | Closed | Sprint 6 | 2025-08-12 18:19 |  | 2025-08-29 15:54
SSMPP003-491 | Job Portal | Bug | The order of job posting list is not from the latest | Closed | Sprint 6 | 2025-08-12 18:31 |  | 2025-08-29 15:54
SSMPP003-492 | Job Portal | Bug | The status of original job request is not changed even though the status of job posting has changed | Closed | Sprint 6 | 2025-08-12 18:38 |  | 2025-08-29 15:54
SSMPP003-493 | Job Portal | Bug | HR has no permission to the rejected requisitions | Closed | Sprint 6 | 2025-08-12 18:50 |  | 2025-08-29 15:54
SSMPP003-498 | Job Portal | Bug | The label "Number of Positions Required" is not changed to "Total Headcount" in Job Posting Creations | Closed | Sprint 6 | 2025-08-13 17:52 |  | 2025-08-29 15:54
SSMPP003-499 | Job Portal | Bug | The application is not sorted based on the submitted/applied date | Closed | Sprint 6 | 2025-08-18 12:33 |  | 2025-08-29 15:54
SSMPP003-500 | Job Portal | Bug | There is no button to view job posting from job requisition detail | Closed | Sprint 6 | 2025-08-18 17:32 |  | 2025-08-29 15:54
SSMPP003-501 | Job Portal | Bug | [FE] Form Edit Job Requisition not pre-populated when editing (redirect) from List Job Requisition | Closed | Sprint 6 | 2025-08-19 13:54 |  | 2025-08-29 15:54
SSMPP003-502 | Job Portal | Bug | The modal 'New Job Request' appears again after user editing the job request successfully | Closed | Sprint 6 | 2025-08-20 15:40 |  | 2025-08-29 15:54
SSMPP003-503 | Job Portal | Bug | The value in the modal 'New Job Request' is not reset after user create a new one successfully | Closed | Sprint 6 | 2025-08-20 15:43 |  | 2025-08-29 15:54
SSMPP003-506 | Job Portal | Bug | The profile page of applicant becomes white blank when it's refreshed | Closed | Sprint 6 | 2025-08-21 12:15 |  | 2025-08-29 15:54
SSMPP003-507 | Job Portal | Bug | The behavior of button 'X' is not correct in applicant profile (Job Portal External), makes misunderstanding | Closed | Sprint 6 | 2025-08-21 12:33 |  | 2025-08-29 15:54
SSMPP003-508 | Job Portal | Bug | The job can be applied even though in the modal or form 'Application Form', the CV is removed | Closed | Sprint 6 | 2025-08-21 12:53 |  | 2025-08-29 15:54
SSMPP003-509 | Job Portal | Bug | The behavior of 'Activate Account' after user create a new account in Job Portal External is not correct | Closed | Sprint 6 | 2025-08-21 13:12 |  | 2025-09-01 18:54
SSMPP003-488 | Job Portal | Test | Verify Link to Published Job Posting from Requisition | Done | Sprint 6 | 2025-08-12 16:48 |  | 2025-08-26 10:36
SSMPP003-489 | Job Portal | Test | Verify View Posting's Original Request | Done | Sprint 6 | 2025-08-12 17:44 |  | 2025-08-13 18:48
SSMPP003-510 | Job Portal | Bug | There is no response after user confirm to 'Hold' and 'Close' from job posting list | Closed | Sprint 6 | 2025-08-21 13:26 |  | 2025-08-29 15:54
SSMPP003-511 | Job Portal | Bug | There is an error message when there is no feedback yet | Closed | Sprint 6 | 2025-08-27 11:37 |  | 2025-08-29 15:54
SSMPP003-512 | Job Portal | Bug | There is no message 'This job posting has been closed and is no longer accepting applications' in job posting external | Closed | Sprint 6 | 2025-08-27 12:10 |  | 2025-08-29 15:54
SSMPP003-513 | Job Portal | Bug | Test Results Score can be inputted until 4 digits but, only can be saved until 3 digits | Closed | Sprint 6 | 2025-08-27 12:36 |  | 2025-08-29 15:54
SSMPP003-495 | Job Portal | Test | Verify Application Progress Tracking | Done | Sprint 6 | 2025-08-13 12:35 |  | 2025-08-25 18:10
SSMPP003-496 | Job Portal | Test | Verify Standardize Headcount Labeling Across Job Requests & Postings | Done | Sprint 6 | 2025-08-13 12:56 |  | 2025-08-18 17:43
SSMPP003-77 | Job Portal | Story | Update Applicant Statuses | Done | Sprint 6 | 2025-03-10 12:29 |  | 2025-08-05 19:04
SSMPP003-93 | Job Portal | Story | View Application Detail | Done | Sprint 6 | 2025-03-19 17:24 |  | 2025-09-01 19:01
SSMPP003-94 | Job Portal | Story | Application Progress Tracking | Done | Sprint 6 | 2025-03-24 15:26 |  | 2025-08-25 18:11
SSMPP003-114 | Job Portal | Story | Link to Published Job Posting from Requisition | Done | Sprint 6 | 2025-04-08 12:53 |  | 2025-08-20 18:14
SSMPP003-115 | Job Portal | Story | View Posting's Original Request | Done | Sprint 6 | 2025-04-08 12:54 |  | 2025-08-13 11:00
SSMPP003-166 | Job Portal | Story | Requisition Reject/Approve Notes | Done | Sprint 6 | 2025-04-24 19:04 |  | 2025-08-12 13:45
SSMPP003-404 | Job Portal | Story | Job Detail (Internal): Break out title, department, project/function into labeled fields | Done | Sprint 6 | 2025-07-08 11:42 |  | 2025-08-08 18:07
SSMPP003-405 | Job Portal | Story | Job Detail (Internal): Add icon beside location field | Done | Sprint 6 | 2025-07-08 11:46 |  | 2025-08-08 18:07
SSMPP003-408 | Job Portal | Story | Tables: Sync column formats between Job Posting and Job Request tables | Done | Sprint 6 | 2025-07-08 12:22 |  | 2025-08-18 10:40
SSMPP003-428 | Job Portal | Story | Change Text: "Salary Range" -> "Budget Min / Max" | Done | Sprint 6 | 2025-07-16 15:17 |  | 2025-08-08 18:07
SSMPP003-439 | Job Portal | Story | Settings: Job Location, Placement, Project | Done | Sprint 6 | 2025-07-22 12:45 |  | 2025-08-08 18:07
SSMPP003-464 | Job Portal | Story | Standardize Headcount Labeling Across Job Requests & Postings | Done | Sprint 6 | 2025-08-01 13:50 |  | 2025-08-18 17:43
SSMPP003-441 | Job Portal | Task | Hide "Apply Link" and "Excel Link" in Job Posting Detail Page | Done | Sprint 6 | 2025-07-23 17:09 |  | 2025-08-08 18:07
SSMPP003-485 | Job Portal | Task | [FE] Hiring Manager Default Selected Value | Done | Sprint 6 | 2025-08-12 13:13 |  | 2025-08-18 11:43
SSMPP003-497 | Job Portal | Task | [FE] integration API Accepted by and Rejected by HR | Done | Sprint 6 | 2025-08-13 13:13 |  | 2025-08-18 11:42
SSMPP003-504 | Job Portal | Task | [FE] Skill matching filter | Done | Sprint 6 | 2025-08-20 18:12 |  | 2025-08-25 12:52
SSMPP003-505 | Job Portal | Task | [FE] Refactor logic for add/create new skill in JR/JP to store the data after user submit the form | Done | Sprint 6 | 2025-08-20 18:14 |  | 2025-08-25 12:52

## risk&issue
Month | Project | Issue & Risk Project | Action
| Project | Issue & Risk Project | Solution