## in
Issue Type | Project lead id | Issue key | Issue id | Summary | Assignee | Priority | Status | Status Category | Created | Updated | Resolution | Resolved | Sprint | Sprint | Sprint
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4110 | 239957 | [MS] Add onHandQty and make changes | Roshan Modi / Encora | High | CODE REVIEW | In Progress | 01/Oct/25 10:19 PM | 02/Oct/25 8:08 AM |  |  | PFO Sprint 14
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3336 | 232731 | Edit response on delivery API | Roshan Modi / Encora | Low | CODE REVIEW | In Progress | 01/Sep/25 2:53 AM | 17/Sep/25 12:09 AM
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4151 | 240262 | [MS][Ord] PaymentHelper unit test | Muhammad Lukmanul Hakim / LG Sinarmas | Low | To Do | To Do | 03/Oct/25 6:02 PM | 03/Oct/25 6:02 PM
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4150 | 240260 | [MS][Ord] CartHelper unit test | Muhammad Lukmanul Hakim / LG Sinarmas | Low | To Do | To Do | 03/Oct/25 6:02 PM | 03/Oct/25 6:02 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4135 | 240140 | Prod : Calendar is not shown properly for RXO Zip codes | Pawan Bhandari / Qualitest | Critical | READY FOR DEPLOYMENT | Done | 03/Oct/25 7:09 AM | 04/Oct/25 9:41 AM | Done | 03/Oct/25 2:58 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3402 | 233239 | [STG]Checkout:Parcel product Incorrect delivery cost for Next_day & Expedited delivery method | Smeet Dhabarde / Encora | Major | READY FOR DEPLOYMENT | Done | 03/Sep/25 6:58 AM | 02/Oct/25 9:28 AM | Done | 19/Sep/25 10:55 AM | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3428 | 233537 | Store Credit - Negative Subtotal After Removing Item from Cart | Pawan Bhandari / Qualitest | Critical | Done | Done | 03/Sep/25 7:11 PM | 17/Sep/25 12:14 AM | Done | 04/Sep/25 6:04 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2474 | 216365 | [QA10] [ORD][MS ] Set payment method: Getting 400 error with incorrect message if We pass "reward_points" option for Guest user cart ID | Smeet Dhabarde / Encora | Low | READY FOR STAGING | Done | 05/Aug/25 10:06 AM | 01/Sep/25 10:03 AM | Done | 01/Sep/25 10:03 AM | PFO Sprint 12
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2485 | 216596 | Implement Product Type Restriction | Roshan Modi / Encora | Low | RE-OPENED | To Do | 05/Aug/25 11:42 PM | 04/Sep/25 4:37 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2481 | 216484 | [QA10] [ORD][MS ] Set payment method: Store credit with Paypal is allowed into Set payment method | Smeet Dhabarde / Encora | High | READY FOR STAGING | Done | 05/Aug/25 2:33 PM | 04/Sep/25 4:35 PM | Done | 11/Aug/25 5:08 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3494 | 234026 | [STG] - Delivery Date & Cost is updating on page refresh | Smeet Dhabarde / Encora | Major | READY FOR DEPLOYMENT | Done | 05/Sep/25 11:26 AM | 17/Sep/25 5:06 AM | Done | 17/Sep/25 5:06 AM | PFO Sprint 14
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2570 | 218123 | Merge Repos into process layer | Roshan Modi / Encora | Low | Done | Done | 07/Aug/25 4:53 PM | 04/Sep/25 8:40 AM | Done | 26/Aug/25 3:54 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1958 | 206859 | [QA10][Delivery API] - Availability/Validate API is showing Incorrect Message if we pass Invalid/Wrong/null Freight Type | Smeet Dhabarde / Encora | Medium | Done | Done | 07/Jul/25 7:35 AM | 04/Sep/25 8:40 AM | Done | 25/Aug/25 3:20 AM | PFO Sprint 12
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3508 | 234281 | [STG] newEstimate date api is failing on PDP page | Smeet Dhabarde / Encora | Medium | READY FOR DEPLOYMENT | Done | 08/Sep/25 4:41 AM | 26/Sep/25 8:50 AM | Done | 15/Sep/25 3:22 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3534 | 234558 | [STG] Store pickup option is not available on pdp/cart | Pawan Bhandari / Qualitest | Blocker | Done | Done | 08/Sep/25 6:21 PM | 17/Sep/25 12:19 AM | Done | 11/Sep/25 10:40 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2633 | 218552 | [QA10][MS] Get Cart: Standard method not available on available delivery option | Xiaoxue Guo / Marlabs | High | Done | Done | 09/Aug/25 4:51 PM | 04/Sep/25 2:28 PM | Done | 25/Aug/25 9:31 AM | PFO Sprint 12
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3565 | 235023 | Update restriction table and logic | Roshan Modi / Encora | High | READY FOR QA | In Progress | 09/Sep/25 9:22 PM | 17/Sep/25 12:21 AM |  |  | PFO Sprint 14
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-105 | 171179 | Delivery Process Service | Roshan Modi / Encora | Low | In Progress | In Progress | 10/Mar/25 9:54 AM | 17/Sep/25 12:25 AM |  |  | PFO Sprint 14
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-111 | 171186 | [MS] Dynamic Scheduling - Update API | Smeet Dhabarde / Encora | Low | READY FOR STAGING | Done | 10/Mar/25 9:57 AM | 01/Sep/25 1:42 AM | Done | 01/Sep/25 1:42 AM | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2649 | 218672 | [STG][QA10] Cart ¦ Delivery date for same product & zipcode is different on OLD & NEW Cart | Smeet Dhabarde / Encora | High | Done | Done | 11/Aug/25 3:12 AM | 28/Sep/25 10:13 PM | Done | 20/Sep/25 9:30 PM | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2027 | 208208 | [QA10][Delivery API] - "Get Estimate" API for is giving additional data in response i.e. "totalEstimatedCost" which is not mentioned into TDD | Roshan Modi / Encora | Medium | READY FOR STAGING | Done | 11/Jul/25 9:14 AM | 04/Sep/25 8:40 AM | Done | 18/Aug/25 7:02 AM | PFO Sprint 11
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3617 | 235440 | [STG][Checkout]: LMD product - Standard delivery option is missing by default & In-Home delivery radio button is not selected | Smeet Dhabarde / Encora | Blocker | READY FOR DEPLOYMENT | Done | 11/Sep/25 6:18 AM | 17/Sep/25 12:25 AM | Done | 12/Sep/25 5:37 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3620 | 235444 | [QA10] Facing slowness in QA10 environment | Hema Deepika Rani / Qualitest | Low | Done | Done | 11/Sep/25 7:06 AM | 28/Sep/25 10:15 PM | Done | 23/Sep/25 7:00 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3659 | 235787 | [STG] - Delivery Date are not getting into calender from available api | Smeet Dhabarde / Encora | Major | Done | Done | 12/Sep/25 11:47 AM | 28/Sep/25 10:11 PM | Done | 22/Sep/25 3:12 AM | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3651 | 235720 | [Stage] Checkout ¦ On calender user is able to see & select earlier delivery date than earliest shipping date | Smeet Dhabarde / Encora | Critical | READY FOR DEPLOYMENT | Done | 12/Sep/25 8:05 AM | 17/Sep/25 12:26 AM | Done | 15/Sep/25 3:12 AM | PFO Sprint 13 | PFO Sprint 15
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3653 | 235730 | [STG] : User is able to add open box products to cart more than product quantity available in PDS DB | Madhuri Chinne / Qualitest | Blocker | READY FOR DEPLOYMENT | Done | 12/Sep/25 8:41 AM | 16/Sep/25 8:50 AM | Done | 16/Sep/25 7:02 AM | PFO Sprint 14
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2801 | 220177 | Get Slot POST API | Roshan Modi / Encora | Low | READY FOR QA | In Progress | 14/Aug/25 3:32 AM | 28/Sep/25 10:13 PM |  |  | PFO Sprint 14
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2060 | 208855 | [Ord][MS] Set Payment Method | Smeet Dhabarde / Encora | Low | READY FOR QA | In Progress | 14/Jul/25 10:45 PM | 16/Sep/25 9:12 AM |  |  | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2839 | 220410 | [QA10] Delivery Service: snapshot API: Delivery Date Null For Specific Zip code | Pawan Bhandari / Qualitest | Blocker | Done | Done | 15/Aug/25 9:09 AM | 08/Sep/25 10:49 AM | Done | 08/Sep/25 10:49 AM | PFO Sprint 13
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2085 | 209441 | [QA10][Delivery API] - POST "Update schedule" API response time is more than 500ms | Pawan Bhandari / Qualitest | Lowest | READY FOR QA | In Progress | 16/Jul/25 7:37 AM | 17/Sep/25 12:19 AM |  |  | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2094 | 209537 | [QA10][Delivery API] - POST "Update Schedule" API giving 200 response with Invalid Phone number | Roshan Modi / Encora | High | Done | Done | 16/Jul/25 9:50 AM | 04/Sep/25 8:40 AM | Done | 18/Aug/25 1:28 PM | PFO Sprint 12
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2926 | 220662 | [QA10] [No Remove Stre Credit Option] PayPal payment is available after applying store credits | Akash Suryawanshi / Qualitest | Critical | READY FOR STAGING | Done | 17/Aug/25 9:42 AM | 17/Sep/25 12:13 AM | Done | 04/Sep/25 2:27 PM | PFO Sprint 13
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2139 | 210214 | [QA10][Delivery API] - For Quote API with "freightType": "LMD" & "shippingMethod": "NEXT_DAY" getting same estimate date of standard shipping | Roshan Modi / Encora | Medium | READY FOR STAGING | Done | 18/Jul/25 7:04 AM | 04/Sep/25 8:40 AM | Done | 16/Aug/25 2:57 AM | PFO Sprint 11
Story | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2987 | 226796 | [MS] Place Order Validation | Yawei (Sigma) Yang / LGE | Low | CODE REVIEW | In Progress | 19/Aug/25 10:31 AM | 28/Sep/25 10:14 PM
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2982 | 226781 | API to get options for delivery. | Roshan Modi / Encora | Critical | READY FOR QA | In Progress | 19/Aug/25 9:47 AM | 04/Sep/25 1:39 PM
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-283 | 173013 | TMS System Service | Roshan Modi / Encora | Low | READY FOR QA | In Progress | 19/Mar/25 2:04 AM | 16/Sep/25 9:12 AM |  |  | PFO Sprint 9 | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3012 | 227002 | [QA10] [OBS Guest] Express Checkout - Date discrepancy for Next Day In-home delivery | Hema Deepika Rani / Qualitest | High | READY FOR STAGING | Done | 20/Aug/25 2:12 AM | 03/Sep/25 9:53 PM | Done | 26/Aug/25 3:30 AM | PFO Sprint 12
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1127 | 193525 | QA10 [Delivery-API] : Estimate API for PLP page is giving NULL data for LMD for few zipcodes (01001,96161,77027,44064) | Smeet Dhabarde / Encora | High | READY FOR STAGING | Done | 20/May/25 8:27 AM | 04/Sep/25 8:40 AM | Done | 01/Sep/25 10:07 AM | PFO Sprint 12
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1135 | 193704 | [Product Service] Create API to fetch Inventory | Roshan Modi / Encora | Low | RE-OPENED | To Do | 20/May/25 9:23 PM | 16/Sep/25 9:12 AM |  |  | PFO Sprint 14
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3821 | 237655 | Change standard PARCEL to FedEx | Akash Suryawanshi / Qualitest | High | READY FOR QA | In Progress | 20/Sep/25 8:02 AM | 28/Sep/25 10:20 PM |  |  | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3076 | 227683 | [QA10] Dynamic Scheduling : LMD Next day delivery is showing todays delivery date | Smeet Dhabarde / Encora | High | READY FOR STAGING | Done | 21/Aug/25 4:13 AM | 03/Sep/25 9:53 PM | Done | 25/Aug/25 8:46 AM | PFO Sprint 12
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3861 | 237748 | [STG/QA10] [BOPIS] Rescheduled delivery button not appearing for bopis+shipping orders & normal shipping orders, DS orders not getting commited | Kishor Kumar Kar / Encora | Medium | RE-OPENED | To Do | 21/Sep/25 8:49 AM | 01/Oct/25 1:17 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2182 | 210966 | [QA10][Delivery API] - For PLP API with 96161 Zipcode getting Null estimated date for PARCEL & LMD freight type | Roshan Modi / Encora | Major | Done | Done | 22/Jul/25 3:51 AM | 20/Sep/25 9:31 PM | Done | 20/Sep/25 9:31 PM | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2188 | 211043 | QA10 [Delivery-API] : Quote API response time is more than 500ms | Pawan Bhandari / Qualitest | Lowest | READY FOR QA | In Progress | 22/Jul/25 9:40 AM | 17/Sep/25 12:19 AM |  |  | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1177 | 194201 | [QA10][MS] - Need information : For Post config ticket/task is missing but in TDD POST "Add Config" method is mentioned | Roshan Modi / Encora | Medium | DEFERRED | Done | 22/May/25 7:02 AM | 01/Sep/25 10:49 PM | Done | 01/Sep/25 10:49 PM | PFO Sprint 5 | PFO Sprint 6 | PFO Sprint 12
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3896 | 237848 | [MS][Ord] CustomerServiceImpl unit test | Muhammad Lukmanul Hakim / LG Sinarmas | Low | Done | Done | 22/Sep/25 10:26 AM | 01/Oct/25 2:45 AM | Done | 01/Oct/25 2:45 AM
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3895 | 237846 | [MS][Ord] CartPaymentServiceImpl unit test | Felix Yuan Fang / Marlabs | Low | Done | Done | 22/Sep/25 10:26 AM | 28/Sep/25 10:19 PM | Done | 26/Sep/25 9:55 AM
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3897 | 237850 | [MS][Ord] PaymentHelperImpl unit test | Felix Yuan Fang / Marlabs | Low | Done | Done | 22/Sep/25 10:27 AM | 28/Sep/25 10:18 PM | Done | 26/Sep/25 9:54 AM
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1200 | 194893 | [talend] lg_vw_product_spec update column in talend for PDS service | Dhanoop Beena Sivan / Infosys | Low | Done | Done | 23/May/25 11:40 AM | 29/Sep/25 9:03 AM | Done | 03/Jun/25 9:30 AM | PFO Sprint 6
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2247 | 211913 | [QA10][Delivery API] - For Quote API with "freightType": "LMD" & Shipping method: standard - getting Data not found error (404) | Smeet Dhabarde / Encora | High | READY FOR STAGING | Done | 24/Jul/25 10:24 AM | 04/Sep/25 8:40 AM | Done | 16/Aug/25 7:02 AM | PFO Sprint 11
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1770 | 203566 | [BOPIS] Create a API to check availability for location store | Roshan Modi / Encora | Low | CODE REVIEW | In Progress | 24/Jun/25 9:34 PM | 16/Sep/25 9:12 AM |  |  | PFO Sprint 14
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3940 | 238163 | [STG][DS] Observe LPTU carrier is called for XPO zip code in the delivery-available-dates API | Saritha Yapadinni / Qualitest | Medium | READY FOR QA | In Progress | 24/Sep/25 3:56 AM | 01/Oct/25 2:43 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3945 | 238180 | [STG][DS] Update / Calendar is not popping up for RXO zip codes | Pawan Bhandari / Qualitest | Medium | READY FOR QA | In Progress | 24/Sep/25 6:56 AM | 03/Oct/25 10:18 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3999 | 238669 | In-Transit Issues | Roshan Modi / Encora | High | In Progress | In Progress | 25/Sep/25 10:16 PM | 02/Oct/25 8:08 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3243 | 231779 | [TASK] Delivery Message for LMD on PDP and Cart – Carrier Down Fallback Handling | Pawan Bhandari / Qualitest | High | Done | Done | 26/Aug/25 2:48 PM | 11/Sep/25 11:09 AM | Done | 11/Sep/25 11:09 AM | PFO Sprint 13
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3208 | 231673 | [QA10] [OBS Guest] /EOS Express Checkout - Date discrepancy for standard and expedited delivery | Smeet Dhabarde / Encora | High | READY FOR STAGING | Done | 26/Aug/25 3:31 AM | 17/Sep/25 12:19 AM | Done | 08/Sep/25 10:46 PM | PFO Sprint 13
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3245 | 231821 | API to get schedule details | Roshan Modi / Encora | Low | CODE REVIEW | In Progress | 26/Aug/25 4:59 PM | 04/Sep/25 8:25 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3224 | 231712 | [QA10] [PM] - On Checkout : Expediated delivery method is not shown for any parcel product | Smeet Dhabarde / Encora | High | READY FOR STAGING | Done | 26/Aug/25 7:30 AM | 17/Sep/25 12:10 AM | Done | 03/Sep/25 9:35 AM | PFO Sprint 13
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3231 | 231725 | API Improvements for Quote API | Roshan Modi / Encora | Low | CODE REVIEW | In Progress | 26/Aug/25 8:53 AM | 17/Sep/25 12:13 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-1213 | 195815 | [QA10][MS] - GET "Carrier warehouse" API response time is more than 500ms | Roshan Modi / Encora | Lowest | RETIRED | Done | 26/May/25 9:30 AM | 04/Sep/25 8:25 AM | Done | 26/Aug/25 4:03 PM | PFO Sprint 12
Subtask | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4002 | 238702 | Add warehouseZipcode in the response | Roshan Modi / Encora | Low | CODE REVIEW | In Progress | 26/Sep/25 4:10 AM | 26/Sep/25 4:25 AM |  |  | PFO Sprint 14
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3258 | 232115 | Handle product sku STORE on query param level | Roshan Modi / Encora | Low | CODE REVIEW | In Progress | 27/Aug/25 11:05 PM | 03/Sep/25 9:56 PM
Task | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3292 | 232243 | Create Address API for express checkout | Urvish Hingu / Encora | Medium | READY FOR QA | In Progress | 28/Aug/25 2:30 PM | 07/Sep/25 9:50 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3263 | 232147 | [STG] Express checkout / Checkout: Next day & Expediated delivery options missing for all Parcel products | Smeet Dhabarde / Encora | Critical | READY FOR DEPLOYMENT | Done | 28/Aug/25 4:53 AM | 17/Sep/25 12:14 AM | Done | 04/Sep/25 10:23 AM | PFO Sprint 13 | PFO Sprint 15
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-3316 | 232359 | [STG] Logged in Member price tag not reflecting on Stage | Utkarshkatiyar / Qualitest | Low | READY FOR DEPLOYMENT | Done | 29/Aug/25 5:55 AM | 30/Sep/25 6:41 AM | Done | 24/Sep/25 3:29 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2354 | 213350 | [QA10][Delivery API] - Quote API - Incorrect estimated delivery cost for For "PARCEL"with : "NEXT_DAY" / "EXPEDITED" delivery - both cost are standard fedx delivery | Smeet Dhabarde / Encora | Critical | READY FOR STAGING | Done | 29/Jul/25 10:00 AM | 04/Sep/25 8:40 AM | Done | 08/Aug/25 12:19 PM | PFO Sprint 11
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2353 | 213331 | [QA10][Delivery API] - Quote API - Incorrect estimated delivery date for For "PARCEL"with : "NEXT_DAY" delivery | Smeet Dhabarde / Encora | Blocker | READY FOR STAGING | Done | 29/Jul/25 9:29 AM | 04/Sep/25 2:20 PM | Done | 08/Aug/25 2:51 AM | PFO Sprint 11
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4062 | 239419 | In-Transit Issues - Incorrect delivery date for LMD item for in-transit stock on PDP and Cart | Pawan Bhandari / Qualitest | High | READY FOR QA | In Progress | 29/Sep/25 10:54 PM | 02/Oct/25 9:28 AM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4063 | 239420 | In-Transit Issues: Product with Only In-Transit Stock - PDP shows Notify Me but on click actually does add to cart | Pawan Bhandari / Qualitest | High | READY FOR DEPLOYMENT | Done | 29/Sep/25 11:14 PM | 03/Oct/25 12:24 PM | Done | 01/Oct/25 6:04 PM
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2367 | 214046 | [QA10][Product service] - "GET product Inventory by SKU API "For Incorrect SKU ID getting 400 response with Internal server error message | Smeet Dhabarde / Encora | Medium | READY FOR STAGING | Done | 30/Jul/25 1:59 AM | 04/Sep/25 3:54 PM | Done | 01/Sep/25 9:59 AM | PFO Sprint 12
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2369 | 214052 | [QA10][Product service] - "GET product Inventory by SKU API "For Incorrect Warehouse code & valid SKU ID getting 200 response with blank response body | Smeet Dhabarde / Encora | Medium | Done | Done | 30/Jul/25 2:39 AM | 04/Sep/25 8:40 AM | Done | 08/Aug/25 4:09 AM | PFO Sprint 11
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-2381 | 214111 | [QA10][Delivery API] - Quote API - availability: false with unexpcted error For "PARCEL"with : "EXPEDITED" as Fedx api giving 500 response | Smeet Dhabarde / Encora | Critical | READY FOR STAGING | Done | 30/Jul/25 7:56 AM | 04/Sep/25 4:28 PM | Done | 25/Aug/25 3:13 AM | PFO Sprint 12
Bug | 712020:5b3bc922-a54c-4e77-830d-0aca2f723654 | PFO-4073 | 239451 | [STG] [Checkout]- For LMD product Next day delivery option missing on checkout | Smeet Dhabarde / Encora | Blocker | READY FOR DEPLOYMENT | Done | 30/Sep/25 4:22 AM | 30/Sep/25 10:42 PM | Done | 30/Sep/25 9:33 AM