## SI
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Sprint | Sprint Schedule | Total Workload | Completed Workload | Defect | Fixed defect | Function Fulfillment Rate | Defect Density | Defect Correction Rate | Comment
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#1 | 2025-03-03 ~ 2025-03-26 | 10 | 10 | 21 | 21 | 100% | 2.1 | 100% | 16 out of 18 tasks have been completed successfully. All 16 identified defects have been resolved.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#2 | 2025-04-08 ~ 2025-05-02 | 8 | 8 | 8 | 8 | 100% | 1 | 100% | All tasks (11) have been completed. 6 defects were detected and have been fully fixed.
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#3 | 2025-05-05 ~ 2025-06-25 | 20 | 18 | 12 | 10 | 90% | 0.66667 | 83.33% | 2 Tasks and 2 Issues are carried over and completed on Sprint 4
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#4 | 2025-06-02 ~ 2025-07-02 | 20 | 16 | 22 | 22 | 80% | 1.375 | 100% | 4 Tasks are carried over to Sprint 5. (3 completed, 1 carried over again to Sprint 6)
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#5 | 2025-07-02 ~ 2025-08-01 | 27 | 17 | 28 | 24 | 62.96% | 1.6471 | 85.71% | 10 Tasks and 4 Bugs are carried over to Sprint 6
| LGSM Career Job Portal | [LGSM] Internal Project |  |  | Sapta Sanjaya | 2 + SF Dev | SI | S#6 | 2025-07-02 ~ 2025-08-01 | 17 | 17 | 31 | 31 | 100% | 1.8235 | 100% | 12 Story and 5 taks have been completed , and 31 defect already fixed. this is last sprint before Job portal going to System Maintenance (SM) project.
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#1 | 2025-04-21 ~ 2025-04-25 | 265 | 265 | 41 | 41 | 100% | 0.15472 | 100% | Sprint #1 - Testing Scenario: Scenario received on May 25, completed on June 25 Total scenarios: 269 Executed: 265 In Progress: 0 Passed: 222 Failed: 41
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#2 | 2025-04-21 ~ 2025-04-25 | 855 | 855 | 28 | 28 | 100% | 0.032749 | 100% | Sprint #2 Total scenarios: 855 Executed: 828 Passed: 776 Failed: 28 Blocked : 24 Untested : 27
| SF Intelligence Unit Testing Project | [GDC] Smart Factory |  |  | Ninan Kara Gicha Nasution | 2 Tester | SI | S#3 | 2025-06-30 ~ 2025-08-14 | 730 | 730 | 1 | 1 | 100% | 0.0013699 | 100% | Sprint #3 Total scenarios: 730 Executed: 729 Passed: 729 Failed: 1
| [Bank Sinarmas] Provision of Card Management System Services | [LDC] Bank Sinarmas |  |  | Andini Margaretta Tarigan |  | SI | S#1 | 2025-09-01 ~ 2025-10-03 | 215 | 241 | 0 | 0 | 112.1% | 0 | #DIV/0! | [Cumulative] - Authorization/Common part : Plan = 72 ¦ Actual = 77 - Front part : Plan = 70 ¦ Actual = 92 - Back-end part : Plan = 73 ¦ Actual = 72 (There was a delay in reflecting the brand incoming file due to work reference checks) Overall Progress = 37.8%
| [Bank Sinarmas] Provision of Card Management System Services | [LDC] Bank Sinarmas |  |  | Andini Margaretta Tarigan |  | SI | S#2 | 2025-10-04 ~ 2025-12-04 | 679 | 656 | 0 | 0 | 97% | 0,00 | N/A | [Cumulative Progress] - Authorization/Common part : Plan = 199 ¦ Actual = 203 - Front part : Plan = 184 ¦ Actual = 181 - Back-end part : Plan = 192 ¦ Actual = 188 - Bank Sinarmas : Plan = 104 ¦ Actual = 87 Overall Progress = 91%

## January
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [6 empty] | 101 | 101 | 0 | 0 | 100% | 0% | #DIV/0!
| SF Automation 2026 | [6 empty] | 75 | 75 | 0 | 0 | 100% | 0 | #DIV/0!
| SF Core Unit 2026 | [6 empty] | 61 | 60 | 1 | 1 | 98.36% | 0.016667 | 100%
| SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | [6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| SF Manufacturing Quality AX Standard Report Utilization Team | [6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| SF Process AX Team 2026 | [6 empty] | 47 | 47 | 0 | 0 | 100% | 0 | #DIV/0!
| SINGLEX Business Unit Testing Project | [6 empty] | 94 | 94 | 1 | 1 | 100% | 0.010638 | 100%
| KB Bank System Maintenance | [6 empty] | 110 | 110 | 1 | 1 | 100% | 0.0090909 | 100%

## February
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [6 empty] | 96 | 96 | 0 | 0 | 100% | 0% | #DIV/0! | Total workload 96 (100% completed) with no defects recorded. Process execution is stable and compliant; however, ensure adequate testing coverage and defect logging to avoid potential under-reporting.
| SF Automation 2026 | [6 empty] | 97 | 78 | 0 | 0 | 80.41% | 0 | #DIV/0! | Total workload 97 (80% completed) indicates delay risk. No defects reported so far; need to review workload completion drivers and ensure no gaps in defect identification during ongoing execution.
| SF Core Unit 2026 | [6 empty] | 127 | 119 | 1 | 1 | 93.7% | 0.0084034 | 100% | Total workload 127 (94% completed) with minimal defect (1) fully resolved (100% fix rate). Indicates controlled quality; recommend root cause analysis to prevent recurrence.
| SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | [6 empty] | 8 | 8 | 0 | 0 | 100% | 0 | #DIV/0! | Total workload 8 (100% completed) with zero defects. Execution appears stable; validate whether testing scope and defect tracking are sufficiently comprehensive.
| SF Manufacturing Quality AX Standard Report Utilization Team | [6 empty] | 3 | 3 | 0 | 0 | 100% | 0 | #DIV/0! | Total workload 3 (100% completed) No defects reported; requires review on progress constraints and testing effectiveness.
| SF Process AX Team 2026 | [6 empty] | 82 | 82 | 3 | 3 | 100% | 0.036585 | 100% | Total workload 82 (100% completed) with 3 defects, all resolved (100% fix rate). Defect density slightly higher but still acceptable; recommend monitoring for process improvement opportunities.
| SINGLEX Business Unit Testing Project | [6 empty] | 98 | 98 | 0 | 0 | 100% | 0 | #DIV/0! | Total workload 98 (100% completed) with no defects. Indicates smooth execution; ensure defect detection process remains effective and not under-reported.
| KB Bank System Maintenance | [6 empty] | 83 | 83 | 0 | 0 | 100% | 0 | #DIV/0! | Total workload 83 (100% completed) with no defects. Stable maintenance execution; continue monitoring to ensure consistent defect identification and reporting.

## Sheet1 (hidden)
Week 1
Cleaning Service Project | 25 - 31 Jan 26 | 0 | 0 | 0 | 0 | 0
SF Automation 2026 | 29 Jan - 04 Feb 26 | 18 | 15 | 0 | 0 | 0
SF Core Unit 2026 | 29 Jan - 04 Feb 26 | 16 | 7 | 0 | 0 | 0
SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | 29 Jan - 04 Feb 26 | 3 | 0 | 0 | 0 | 0
SF Manufacturing Quality AX Standard Report Utilization Team | 29 Jan - 04 Feb 26 | 0 | 0 | 0 | 0 | 0
SF Process AX Team 2026 | 29 Jan - 04 Feb 26 | 56 | 17 | 0 | 0 | 0
SINGLEX Business Unit Testing Project | 26 - 30 Jan 26 | 36 | 36 | 112 | 0 | 0
KB Bank System Maintenance | 26 - 30 Jan 26 | 45 | 45 | 0 | 17 | 7
[Bank Sinarmas] Provision of Card Management System Services | 23 - 29 Jan 26 | 26 | 27 | 482 | 20 | 12
week 2
Cleaning Service Project | 25 - 31 Jan 26 | 43 | 43 | 0 | 0 | 0
SF Automation 2025 | 05 - 11 Feb 26 | 17 | 10 | 0 | 0 | 0
SF Core Unit 2025 | 05 - 11 Feb 26 | 26 | 21 | 0 | 0 | 0
SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | 05 - 11 Feb 26 | 3 | 0 | 0 | 0 | 0
SF Manufacturing Quality AX Standard Report Utilization Team | 05 - 11 Feb 26 | 0 | 0 | 0 | 0 | 0
SF Process AX Team 2025 | 05 - 11 Feb 26 | 37 | 11 | 0 | 0 | 0
SINGLEX Business Unit Testing Project | 02 - 06 Feb 26 | 39 | 39 | 124 | 1 | 1
KB Bank System Maintenance | 02 - 06 Feb 26 | 18 | 15 | 0 | 3 | 3
[Bank Sinarmas] Provision of Card Management System Services | 06 - 12 Feb 26 | 38 | 36 | 483 | 20 | 13
Week 3
Cleaning Service Project | 09 - 13 Feb 26 | 40 | 40 | 0 | 0 | 0
SF Automation 2025 | 12 - 18 Feb 26 | 12 | 9 | 0 | 0 | 0
SF Core Unit 2025 | 12 - 18 Feb 26 | 43 | 34 | 0 | 0 | 0
SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | 12 - 18 Feb 26 | 2 | 1 | 0 | 0 | 0
SF Manufacturing Quality AX Standard Report Utilization Team | 12 - 18 Feb 26 | 0 | 0 | 0 | 0 | 0
SF Process AX Team 2025 | 12 - 18 Feb 26 | 54 | 37 | 0 | 3 | 3
SINGLEX Business Unit Testing Project | 09 - 13 Feb 26 | 23 | 23 | 89 | 2 | 2
KB Bank System Maintenance | 09 - 13 Feb 26 | 11 | 11 | 0 | 4 | 4
[Bank Sinarmas] Provision of Card Management System Services | 13 - 19 Feb 26 | 38 | 37 | 483 | 20 | 13
Week 4
Cleaning Service Project | 15 - 21 Feb 26 | 13 | 13 | 0 | 0 | 0
SF Automation 2025 | 19 - 25 Feb 26 | 33 | 32 | 0 | 0 | 0
SF Core Unit 2025 | 19 - 25 Feb 26 | 71 | 53 | 0 | 1 | 1
SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | 19 - 25 Feb 26 | 1 | 1 | 0 | 0 | 0
SF Manufacturing Quality AX Standard Report Utilization Team | 19 - 25 Feb 26 | 0 | 0 | 0 | 0 | 0
SF Process AX Team 2025 | 19 - 25 Feb 26 | 21 | 3 | 0 | 0 | 0
SINGLEX Business Unit Testing Project | 16 - 20 Feb 26 | 0 | 0 | 0 | 0 | 0
KB Bank System Maintenance | 16 - 20 Feb 26 | 9 | 7 | 0 | 2 | 2
[Bank Sinarmas] Provision of Card Management System Services | 13 - 19 Feb 26 | 38 | 37 | 483 | 20 | 13

## March
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [6 empty] | 50 | 50 | 0 | 0 | 100% | 0% | #DIV/0! |  | 26 | 26 | 0 | 0 | 24 | 24 | 0 | 0
| SF Automation 2026 | [6 empty] | 105 | 105 | 0 | 0 | 100% | 0 | #DIV/0! |  | 21 | 20 | 0 | 0 | 19 | 19 | 0 | 0
| SF Core Unit 2026 | [6 empty] | 98 | 95 | 0 | 0 | 96.94% | 0 | #DIV/0! |  | 34 | 24 | 0 | 0 | 35 | 21 | 0 | 0
| SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | [6 empty] | 12 | 12 | 0 | 0 | 100% | 0 | #DIV/0! |  | 8 | 5 | 0 | 0 | 3 | 1 | 0 | 0
| SF Manufacturing Quality AX Standard Report Utilization Team | [6 empty] | 35 | 35 | 0 | 0 | 100% | 0 | #DIV/0! |  | 29 | 4 | 0 | 0 | 8 | 8 | 0 | 0
| SF Process AX Team 2026 | [6 empty] | 157 | 156 | 6 | 6 | 99.36% | 0.038462 | 100% | 1 task is still in testing by korea team | 48 | 24 | 1 | 1 | 90 | 61 | 5 | 5
| SINGLEX Business Unit Testing Project | [6 empty] | 77 | 77 | 1 | 1 | 100% | 0.012987 | 100% |  | 38 | 38 | 0 | 0 | 39 | 39 | 1 | 1
| KB Bank System Maintenance | [6 empty] | 22 | 21 | 0 | 0 | 95.45% | 0 | #DIV/0! |  | 16 | 15 | 0 | 0 | 6 | 6 | 0 | 0

## April
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [6 empty] | 112 | 112 | 0 | 0 | 100% | 0% | #DIV/0! |  | 22 | 22 | 0 | 0 | 18 | 18 | 0 | 0 | 18 | 18 | 0 | 0 | 21 | 21 | 0 | 0 | 33 | 33 | 0 | 0
| LGUS AWS MSP Project | LGUS AWS MSP Project | [5 empty] | 13 | 11 | 0 | 0 | 84.62% | 0% | #DIV/0! | [13 empty] | 3 | 3 | 0 | 0 | 10 | 8 | 0 | 0
| SF Automation 2026 | [6 empty] | 35 | 35 | 0 | 0 | 100% | 0 | #DIV/0! |  | 66 | 62 | 0 | 0 | 16 | 8 | 0 | 0 | 14 | 13 | 0 | 0 | 26 | 26 | 0 | 0 | 15 | 11 | 0 | 0
| SF Core Unit 2026 | [6 empty] | 51 | 51 | 0 | 0 | 100% | 0 | #DIV/0! |  | 7 | 7 | 0 | 0 | 16 | 16 | 0 | 0 | 18 | 18 | 0 | 0 | 15 | 15 | 0 | 0 | 15 | 14 | 0 | 0
| SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | [6 empty] | 10 | 10 | 0 | 0 | 100% | 0 | #DIV/0! |  | 1 | 1 | 0 | 0 | 6 | 6 | 0 | 0 | 4 | 2 | 0 | 0 | 4 | 3 | 0 | 0 | 5 | 5 | 0 | 0
| SF Manufacturing Quality AX Standard Report Utilization Team | [6 empty] | 34 | 34 | 0 | 0 | 100% | 0 | #DIV/0! |  | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 20 | 18 | 0 | 0
| SF Process AX Team 2026 | [6 empty] | 69 | 69 | 5 | 5 | 100% | 0.072464 | 100% |  | 33 | 33 | 1 | 1 | 29 | 20 | 1 | 1 | 23 | 20 | 0 | 0 | 59 | 55 | 0 | 0 | 64 | 38 | 1 | 1
| SINGLEX Business Unit Testing Project | [6 empty] | 177 | 177 | 8 | 8 | 100% | 0.045198 | 100% |  | 41 | 41 | 2 | 2 | 56 | 56 | 2 | 2 | 32 | 32 | 1 | 1 | 29 | 29 | 2 | 2 | 19 | 19 | 1 | 1
| KB Bank System Maintenance | [6 empty] | 83 | 78 | 8 | 7 | 93.98% | 0.10256 | 87.5% |  | 18 | 17 | 1 | 1 | 27 | 26 | 1 | 0 | 10 | 10 | 3 | 3 | 7 | 6 | 1 | 1 | 21 | 19 | 2 | 2

## May
Project ID | Project Name | IDB Team | Start date | End Date | Project Leader or PIC | No of Employee | Project Type | Total Workload | Completed Workload | Defect | Fixed defect | Productivity Rate Rate | Defect Density | Defect Correction Rate | Comment
| Purchasing Enhancement Project | [6 empty] | 61 | 58 | 0 | 0 | 95.08% | 0% | #DIV/0! |  | 33 | 30 | 0 | 0 | 28 | 28 | 0 | 0
| LGUS AWS MSP Project | [6 empty] | 14 | 14 | 0 | 0 | 100% | 0% | #DIV/0! |  | 8 | 8 | 0 | 0 | 6 | 6 | 0 | 0
| SF Automation 2026 | [6 empty] | 132 | 132 | 0 | 0 | 100% | 0% | #DIV/0! |  | 43 | 40 | 0 | 0 | 6 | 4 | 0 | 0
| SF Core Unit 2026 | [6 empty] | 50 | 44 | 0 | 0 | 88% | 0% | #DIV/0! | 2 task still in code review, 4 task in progress | 15 | 14 | 0 | 0 | 8 | 5 | 0 | 0
| SF Manufacturing Quality AX RMS/MIMS Operation & Development Team | [6 empty] | 12 | 11 | 0 | 0 | 91.67% | 0% | #DIV/0! | 1 task in development | 6 | 5 | 0 | 0 | 2 | 2 | 0 | 0
| SF Manufacturing Quality AX Standard Report Utilization Team | [6 empty] | 17 | 17 | 0 | 0 | 100% | 0% | #DIV/0! |  | 6 | 6 | 0 | 0 | 12 | 12 | 0 | 0
| SF Process AX Team 2026 | [6 empty] | 139 | 133 | 4 | 4 | 95.68% | 3.008% | 100% |  | 26 | 24 | 0 | 0 | 22 | 18 | 0 | 0
| SINGLEX Business Unit Testing Project | [6 empty] | 64 | 64 | 2 | 2 | 100% | 3.125% | 100% | 2 task in development , 4 task in testing by korea team | 25 | 25 | 1 | 1 | 39 | 39 | 1 | 1
| KB Bank System Maintenance | [6 empty] | 47 | 39 | 8 | 8 | 82.98% | 20.51% | 100% |  | 20 | 18 | 3 | 3 | 27 | 21 | 5 | 5

## Quality Metrics
Project Type | Project evaluation will be conducted based on comprehensive "Project Quality Metrics," with the update frequency and evaluation approach tailored to the project type:
SI | For SI (System Integration) projects, which involve building a new system from scratch, evaluations will be updated after every sprint to closely monitor development progress, quality, and issue resolution during incremental delivery phases.
SM | For SM (System Maintenance) projects, focused on maintaining and improving existing systems, evaluations will be updated monthly, allowing a broader view of ongoing system health and maintenance activities over time.
Quality Metrics
Indicator | Productivity Rate | Quality Rate
| Function Fulfilment Evaluation | Bug Density | Bug Correction Rate
Risk | Completed requests ≤ 70% | Bug density ≥ 3 or Bug correction rate ≤ 70%
Issue | Completed requests ≥ 70% and < 80% | Bug density ≥ 2 or Bug correction rate > 70% and ≤ 80%
Standard | Completed requests ≥ 80% | Bug density < 2 or Bug correction rate > 80%
Metric Definitions and Impact on Project Types
Functional Fulfillment: | Measures how much of the requested functions have been completed relative to the total planned functions for the project or component.
Bug Density | Number of bugs found relative to the size of the project/component - critical for both new development (SI) and ongoing maintenance (SM).
Bug Correction Rate: | Percentage of bugs fixed within the evaluated period, indicating responsiveness and maintenance quality.